## Sheet1
ID | Title | Authors | Year | Description
RISK-3602 | (Presentation Only) Managing Risk and Uncertainty for Large and Small Projects | Dr. Nick J. Lavingia, PE | 2021 | The goal of a project development and execution process is to select the right project and execute that decision with excellence. This practical presentation addresses how decision & risk analysis is used in the industry to make informed decision by comparing alternatives, quantifying risks & uncertainties and evaluating financial outcomes. Tools such as decision hierarchy, strategy table, influence diagram, tornado chart, decision tree and S-curve will be presented and how they are used to make complex decision on actual large as well as small projects.
RISK-3649 | Comparative Risk Analysis Method | Alexandre Rabello David, Sr. | 2021 | This is a methodology designed to determine CAPEX differences for the implementation of the same project, through the comparison of risk perception from different perspectives. The methodology, called comparative risk analysis method, consists of determining different confidence intervals to be applied to CAPEX necessary for project implementation, considering a given scope and varied modeling on how to implement. Alternative forms of contracting and contractual obligations are explored as models. For the performance of the simulations, weights are assigned to different levels of impacts and the Monte Carlo method is applied. As a result, a confidence interval is generated for each modeling considered in the simulation, so that there will be a specific CAPEX for each modeling and its percentile of the distribution curve. The comparative risk analysis method can be considered as another alternative to be joined to existing methodologies for determining confidence intervals and contingencies.
RISK-3658 | Uncertainty Management Includes Risk Management | A. Hilje Langeland | 2021 | This paper describes the Norwegian best practice method of uncertainty management, including how it works and some of its results. Uncertainty analyses of investment costs are a key component of the decision-making basis (decision & risk management (DRM)) in project management and portfolio management and a central component of quality reviews conducted before decisions are reached in major government projects. Uncertainty analyses are used in an interdisciplinary advisory capacity and for quality review purposes. They are used by Norwegian companies, project portfolios, the real estate industry, and government ministries. While average overruns of investment cost (CAPEX) reported in international studies typically have been over 30 percent, or between 12 and 24 percent, Norwegian studies report average overruns of two percent. The motivation behind this paper is the observation that projects practicing uncertainty management appear to reduce project cost overrun and increase project success rates. The method practiced in Norway has some methodological differences from the one presented by John K. Hollmann and in traditional risk management methods. Risk management is an integral part of uncertainty management. Over the last 20 years it has been different challenges related to combine risk management and uncertainty management. These changing, complex and uncertain times require better, integrated leadership, and the value of handling risk and uncertainty has increased. The author therefore wishes to share this best practice knowledge with AACE members. The COVID-19 pandemic has also granted the uncertainty management process, with its high-quality digital facilitations, and the opportunity to improve the analytical process independent of geographical area.
RISK-3689 | Integrated Cost-Schedule Risk Analysis: Application of Project Risk Twin Process for Major Infrastructure Projects using RIAAT (Digital Twin) | Dr. Philip Sander; Dr. Michael Essig; John J. Reilly, PE | 2021 | Digital twin (DT) – a representation of an object or process from the real into the digital world. Key aspects are the transfer of data and the ability to run simulations as to predict possible future outcomes. This term is also used to describe digital models of large infrastructure projects as in recent years there have been significant technological advances in the areas of modeling and simulation. The same applies to the great progress that has been made in the integrated modeling of project cost, schedule and the risks associated with these projects. This paper discusses the project risk twin (PRT) process, which considers the correct application of integrated cost and schedule risk analysis with additional advanced features such as risk correlations, dependencies and linkage, event tree analysis, Poisson distributions for multiple risk occurrences, calculation of potential future delay cost (i.e., liquidated damages and penalty cost), and escalation. The PRT process accompanies the project throughout the planning, construction and operation phase. Key benefits are understanding, analyzing and proactively mitigating risks, avoiding construction delays and developing and seizing opportunities. This is achieved through the application of advanced modeling techniques and simulation to predict future outcomes. Demonstration of an application of the PRT and the abovementioned features are presented in the case study. The model is built up and visualized using RIAAT (risk administration and analysis tool) software. The PRT process discussed in this paper is consistent with the AACE Recommended Practice “57R-09: Integrated Cost and Schedule Risk Analysis Using Risk Drivers and Monte Carlo Simulation of a CPM Model”. The paper also highlights additional features of the PRT process not covered by RP 57R-09.
RISK-3699 | The Value of Prioritization Criteria to Federal Agencies | Abiodun Ajayi; Samantha O’Donnell; Jonathan Maschio; Auguste Boova; Jodie Kim, PE; Michael Donoghue | 2021 | Organizations often struggle to determine their project portfolio requirements, select the right projects to execute, and provide justification for the formation of the capital budget. To combat this, they should develop a portfolio prioritization approach that focuses on ways to quantifiably rank projects against each other while considering risks and priorities of the organization. A portfolio prioritization approach should include detailed budget information that can be drilled down by program, project type, and appropriation type to enhance transparency in funding allocations, enable rapid development of reports to answer budget questions efficiently and correctly, and inform management for data-driven decision-making. This approach would include existing project information and the application of a scoring methodology to weigh the risks and priorities of a project and determine its eligibility for funding. The output can allow agencies to compare funded and unfunded requirements, make informed decisions on projects to execute, and determine how to allocate or reallocate budget for capital planning. Such a portfolio prioritization approach has been used at several federal agencies. This paper explores how risk and priority assessment criteria allow for an effective prioritization of projects with quantifiable outcomes and an optimized capital spend plan. Further, this studies the applicability and scalability of these prioritization criteria at other agencies using a predictive analysis.
RISK-3703 | Construction Value Chain Investments to Achieve Social Return on Investment | Auguste Boova; Eric Dembert; Corey Edson; Rahul Gupta; Shanna Hawley; Tim Kelly; Jodie Kim, PE | 2021 | The construction industry is a historically competitive market driven by multiple players, including building owners, designers, and builders motivated primarily by financial return. Representing more than 8 percent of the global GDP [0], the construction industry has continued to grow as skyscrapers and large complexes emerge in even more suburban and rural areas. The industry, however, has not been immune to the COVID-19 pandemic, as the white-collar workforce has shifted to a remote working environment while also giving up their high-rise apartments for more affordable homes in less populated areas. As a result, many workspaces are left unused as occupancy rates plummet. To combat the decrease in demand for the physical workspace, construction and real estate players may need to adjust their business models to incentivize consumers to reoccupy spaces. The realigned focus on improving and protecting the well-being of occupants requires a shift by all members of the construction value chain to focus on social returns on investments (SROI). This paper will evaluate perspectives on the benefits of achieving SROI and the types of investments that each key player of the construction industry—owners, designers, and builders—needs to make to disrupt the value chain.
RISK-3751 | The Case for Parametric Quantification of Systemic Risks for Transportation Projects | John K. Hollmann, PE CCP CEP DRMP FAACE Hon. Life | 2021 | AACE® International recommended practices (RPs) address empirically-based, risk-driven parametric modeling to quantify systemic risks. These RPs reflect the process industry’s embrace of phase-gate project systems and extensive research supporting the methods. While the cost overrun-prone transportation sector is catching up in applying phase-gate systems, it lags in benchmarking and research and has been detoured away from the RP methods. Research showing that fundamental practice failures (i.e., systemic risks) cause cost growth has been largely ignored. Instead, an unsupported hypothesis as to the cause of cost overruns called the planning fallacy (i.e., optimism bias or lying), and a pessimistic “de-biasing” practice called reference class forecasting (RCF) are being embraced by some in transportation. The danger is that RCF will institutionalize mediocrity of cost outcomes; a detour to an economic dead end. A principle called the fifth hand, reflecting situational-specific, mixed causes of cost overrun, that aligns with research and AACE RPs, is reviewed. However, what is missing from the debate is the fact that too-narrow estimate accuracy range expectations are wired into owner phase-gate procedures. Estimators use subjective risk analysis that underestimates contingency because it meets these expectations; i.e., the planning fallacy is institutionalized. Those who benefit from low estimates need not lie; just announce a project early in perfect confidence that estimators have failed to put a price on poor scope definition. The paper subtitle should be “we have met the enemy and he is us”. The paper reviews the cost overrun situation, the theories, the research and the various proposed and recommended methods. Despite all evidence to the contrary, the author is hopeful that empirically-valid risk quantification and contingency setting practices will become more widely used, putting an end to endemic cost overruns in the transportation industry.
RISK-3799 | An Advanced Risk Analysis using the Von Neumann and Morgenstern (VNM) Utility Function | Brahim Seddiki, CCP | 2022 | This technical paper will examine, assess, and validate an essential key deliverable that has a significant importance to project control practitioners, such as project budget cost baseline. Thus, a baseline has to be realistic, accurate, and able to reflect correctly future monthly expenditures in which cost performance measures are evaluated against it, and changes can be tracked [1, p15]. The development of such critical outcome can be achieved in two steps: Traditional approach which can be categorized as a qualitative analysis, where expert judgment’s inputs play crucial role in defining high-level baseline based on historical project’s data availability, and any relevant information that may exist at the initial project planning stage. The second step is the subject of the underlying technical paper, which is simply a quantitative analysis approach. Given the monthly planned cost as described in step one, may not be the perfect cost distribution for project control practitioners to rely-on. Thus, this technical paper, proposes an advance methodology, using mathematical modeling, and exhibit a new way on how to substantiate a cost distribution baseline based on, two main cornerstones theory: - Decision-making under uncertainty, using Von Neumann-Morgenstern (VNM)’s expected utility function concept, which has its origin back in 1700 during Nicolas Bernoulli’s era. - Portfolio optimization, using Harry Markowitz, mean-variance portfolio analysis. Utility function, risk appetite, risk tolerance, beta systematic risk, certainty equivalent, risk premium, Sharpe ratio, signal to noise ratio, and risk adjusted value, are the main terminology used to demonstrate and validate the cost baseline.
RISK-3803 | Implementing Qualitative Project Risk Management | Jessica M. Colbert, PRMP PSP; Kimberly D. Forbes, PSP | 2022 | Everyone can remember that one perfect, flawless project, right? No? Neither can the authors. Projects are messy and challenging, full of risks that threaten its schedule and budget. Risk management is a critical component to project success, yet so many project teams and organizations fail to put it into practice. If an organization has no formal risk program or is early in its implementation, project risk management can be inconsistent and often ineffective. This paper explores various strategies to implement qualitative risk management on any project, discover how qualitative risk management can be injected into typical project processes without consuming significant resources or budget and develop strategies for continued use throughout the project life cycle and for historical management. These project-level implementation strategies can later evolve to quantitative risk management at the project level and formal enterprise level programs. Finally, the authors discuss common hurdles project teams experience with risk management implementation and solutions to prevent or overcome these challenges.
RISK-3812 | Choosing Between Strategic Alternatives Using Risk Analysis in Decision Modelling of Project Alternatives | Dr. David T. Hulett, FAACE; Keith D. Hornbacher | 2022 | Project organizations make decisions about projects including whether to pursue the project, its technical configuration, how to organize it, locate it, finance it, what “done” means, how long will it take and how much will it cost. These decisions take studies, analyses of alternatives and expert judgment before the project is sanctioned. During the gestation period for any significant project strategic decisions are being made, and one of the main considerations will include the balance of risk in any alternative. This paper addresses analyzing risk in a decision model simplified to highlight the important risks that make a difference about which project to do, its configurations and indeed whether to do a project at all. The purpose of this paper is to describe and discuss some of the risk analysis tools that can be used when these important scoping strategies are being developed by senior management of any project-oriented organization. These important decisions are made well before there is a project plan, schedule and cost estimate. The paper proposes to develop models simplified to highlight the key risk events of an alternative under consideration and some tools that are available currently to address them. These tools bring clarity, transparency, traceability, repeatability and consistency with recommended practices of project risk analysis. Simple models were developed to illustrate two of these methods, probabilistic branching and conditional branching. One of the desired outcomes is to introduce these methods and their use to organizational senior management and engage them in the tools’ development for their project.
RISK-3822 | Principles for Quantitative Project Risk Management | Dr. David T. Hulett, FAACE; James E. Arrow, DRMP | 2022 | Affordable, powerful computing and the widespread availability of quantitative risk analysis (QRA) software has helped democratize data analytics in project delivery. This, in itself, is great for the project controls profession and industry at large. However, problems arise when: a) project simulations are created without a thorough appreciation of the need for ongoing or continuing project risk management (CPRM), b) risk analysts embark on risk computing before establishing the foundation in a competent SRA-ready schedule, c) identities and parameters about risks are collected within an environment where individual SMEs cannot or will not provide their candid opinions, or more simply, d) risk terminology or processes are invoked that generate bias or noise, undermining risk data quality, potentially, creating more harm than good. This paper will describe the means for ensuring a mathematically unambiguous and traceable rationale for establishing contingency, with relevance that extends into and throughout project delivery, providing protection against known risk and resilience in the face of emerging risk. This approach is underpinned by integrated cost and schedule risk analysis as the primary method of modeling before project approval and, conducted in such a way that minimizes motivated reasoning and establishes a data feedback loop to support: 1) quantitative risk management (QRM), 2) increasingly predictable projects outcomes and, ultimately, 3) a risk-based competitive advantage.
RISK-3824 | Calibration Assessments: Validation of Subjective Probabilities and Impact Ranges in Risk Analysis | Francisco Cruz Moreno, PE | 2022 | Risk analysts and project teams must rely on expert judgment to collect subjective probabilities and ranges of potential cost and schedule impacts, especially when they are performing quantitative risk analyses. The main reason for using subject matter experts is the lack of reliable historical data associated with risk impacts. Research shows that subjective probabilities and risk impact ranges consistently yield overconfident and underconfident results, which, in turn, generate inaccurate cost values at selected confidence levels and confident intervals. This paper explores the limitations of current elicitation approaches to collect and use subjective probabilities and impact ranges to assess uncertainty and risks. It provides several examples of different calibration assessment results and their adequate use to improve the strength of risk input data. It also presents a case for risk analysts to use sound scientific rigor in respect to inputs when performing qualitative risk assessments and quantitative risk analyses in support of decision-making. The author suggests the use of calibration assessment in any modeling approaches using subjective inputs whether they be decision trees, parametric models, Monte Carlo simulation, reference class forecasting, or system dynamics.
RISK-3826 | Doing More with Less: A Data-Driven Approach to Resource Management | Avi Schwartz; Eric Dembert; Corey Edson; Samantha O'Donnell; Yue Ou; Kimberley Civil | 2022 | Organizations throughout the construction industry are being challenged with managing complex project portfolios with limited resources. This issue has been amplified by the COVID-19 pandemic, as demand in both the residential and commercial construction industries has substantially increased, causing builders to turn away work due to their human capital constraints and surging capacity. Despite resource availability and allocation being common challenges, project managers often lack the tools to identify, anticipate, and communicate resource needs and constraints. The implementation of a dynamic approach to resource analysis can enable project managers to better track, monitor, and forecast resource demand for their project portfolio by proactively identifying and mitigating risks impacting the project plan. When critical resources are overallocated and additional talent is required, project managers can easily quantify data-driven decisions to their leadership. Ultimately, this data-driven approach can help provide a healthy and sustainable resource outlook, enabling the project team to deliver efficiently and effectively, while helping to reduce the risk of attrition due to burnout. This paper will detail some of the benefits of implementing a resource-analysis strategy, as well as showcase pilots where this approach has been demonstrated for federal agencies.
RISK-3834 | Cost Contingency as the Standard Deviation of the Cost Estimate: An Extension | Dr. Geoffrey S. Rothwell | 2022 | This paper extends a 2005 article in Cost Engineering: It shows that the level of contingency is an inexact function of (1) the standard deviation of the cost estimate, (2) the approximate accuracy range of the cost estimate, (3) the level of confidence that the cost will be within the accuracy range, and (4) the risk aversion of the parties paying (e.g., client) or monitoring (e.g., regulator) the cost being estimated. While some of the cost engineering literature suggests cost estimates in a specified range, for example, ±30% with an 80% confidence, the accuracy range could be more or less than ±30% and confidence could be more or less than 80%. Larger standard deviations and accuracy ranges and greater confidence levels imply larger contingencies. If there is no consideration of size (or value) of the project or size (or value) of the firm undertaking the project, then cost estimate user’s risk aversion can be modeled as a constant. Taken together, the standard deviation, accuracy range, confidence, and the risk aversion coefficient provide an understanding of the appropriate cost contingency, but do not dictate its value.
RISK-3847 | The Development of Corrected and Summarized Schedules to Support Monte Carlo Simulation | Dr. David T. Hulett, FAACE; Waylon T. Whitehead | 2022 | Project schedules often have factors imposed on them which degrade them as tools for quantitative schedule risk analysis using Monte Carlo simulation (MCS). The contractor’s detailed proposal schedules frequently employ mechanisms encompassing commercial goals, rendering them unsuitable for use in quantitative risk modeling. A good bit of effort is typically required to convert these schedules into reliable tools for risk modeling. This paper describes these problems and develops processes for identifying them and repairing them to withstand the rigors of simulation. It discusses why such findings often lead to creating summary schedules that strictly adhere to best practices while representing the overall project plan rather than de-bugging the contractor’s detailed schedule. Using standards for critical path method (CPM) scheduling implies that what is needed to support MCS is to follow best practice CPM guidelines. Some of those guidelines have pronounced impacts on the conduct of MCS-based schedule risk analysis. This paper highlights and explains these practices and argues that the best way to proceed with a schedule risk analysis is to create a simpler, smaller, but entirely compliant summary schedule rather than simulate the project’s detailed schedule with its flaws.
RISK-3851 | Continuous Improvement of the Project Plan by Effective Use of Execution Scenario Planning | Stephen Uhl | 2022 | Traditional scenario planning has been used by many corporations to help envision plausible alternatives futures, as a way of enhancing decision-making at the business unit or corporate level. These concepts can also be applied effectively in the project execution context. By systematically applying scenario planning to project definition and execution, managers can develop signposts, contingency plans, and alternate strategies to manage major change.
RISK-3859 | Using an Industry Parametric Risk Analysis Model to Assess Recommended Cost Accuracy Ranges | Carlos Henrique Nobre Magalhães; Cocis Alexandre dos Santos Balbino, P.Eng.; Leonardo Muller, CCP PSP; Sued dos Prazeres Santos | 2022 | It is not uncommon for company procedures and project teams in the process industry to directly use the tabulated expected cost accuracy ranges from Recommended Practice (RP) 18R-97 Cost Estimate Classification System – As Applied in Engineering, Procurement, and Construction for the Process Industries in their estimates, with the incorrect presumption that the range is solely determined by the level of scope definition (i.e., the class of the estimate). This article, based on the Rand Corporation (RAND) parametric cost model for risk analysis and contingency determination from RP 43R-08 Cost Estimate Classification System – As Applied in Engineering, Procurement, and Construction for the Process Industries, evaluated model inputs for distinct project scenarios and compared model outcomes with the expected ranges shown in RP 18R-97’s table 1. Built on sample information from the original RAND study (as was done in RP 119R-21, Cost Estimate Accuracy Range and Contingency Determination using Tables Derived from Parametric Risk Models), six scenarios were simulated for scope definition ratings equivalent to FEL 1/Class 5, FEL 2/Class 4 and FEL 3/Class 3, with the manipulation of the model’s other parameters of ‘new technology’, ‘impurity’ and ‘plant complexity’. Results, based solely on these systemic risks, demonstrated frequent RAND model variation from the RP 18R-97 upper ranges when some of the non-definitional risk parameters are reasonably varied. In extreme cases, difficulties were observed in using the Excel NORMINV function to determine the ranges for a parametric model. This paper presents an experimentation of the RAND cost model and demonstrates quantitatively how much model results can diverge from the range-of-ranges tabulated in RP 18R-97.
RISK-3908 | Risk Analysis and Contingency Estimating for Class 10 Estimates | John K. Hollmann, PE CCP CEP DRMP FAACE Hon. Life | 2022 | The AACE® International (AACE) cost estimate classification system recommended practice (RP) series is likely its most recognized RPs. In 2021, a new Unclassified/Class 10 estimate type was introduced in AACE RP 111R-20, Estimating for Long-Range Planning – As Applied for the Public Sector. However, there is no AACE RP for quantitative risk analysis (QRA) methods for estimating contingency or management reserve allowances for Unclassified/Class 10 estimates. A goal of the paper is to lay the groundwork for a potential QRA RP for Unclassified/Class 10 QRA recommended practice. It starts by reviewing the concepts of estimate classification in general and Unclassified/Class 10 estimates in particular. Next, it outlines various uses of these estimates such as for asset life cycle cost (LCC) estimating and analysis as part of strategic portfolio management or for surety (bonding) valuation. The paper also reviews scenario analysis and other decision analysis methods to identify potentially useful QRA concepts. It also reviews current contingency determination practices for long-range estimates and the limited research on long-range estimate cost growth. Finally, several proposed Unclassified/Class 10 QRA and contingency/reserve allowance determination methods, aligned with AACE QRA principles, are presented.
RISK-3914 | The Importance of Doing a Risk Assessment in Every Project, Early and Often | Francisco Cruz Moreno, PE; Gino Napuri, EVP | 2022 | Is there a benefit to executing a project risk assessment early and repeating it often? The definitive answer is yes! Developing and executing a risk assessment early in a project reduces the risk of dealing with project threats and opportunities in an unprepared and chaotic fashion when they do occur. Awareness of time, cost, and/or scope risk impacts on a project is crucial. Understanding the extent to which risk affects a project in a planned and coordinated effort improves the probability of successfully completing a project on time and within budget. It comes as no surprise that the majority of projects fail their estimates to complete as most projects do not execute risk assessments early and often. While other issues may impact a project and lead to failure in addition to omitting proper risk assessments, the inability to manage risk through constant risk assessments is a pivotal reason for failure. This paper will focus on a process that assists the project team in avoiding the continuous failure of completing a project on time, on budget, and within scope because of a lack of proper risk management. If will also provide suggestions to help avoid risk pitfalls by executing risk assessments in a continuous and consistent pace, not only when the risk arises, but from the beginning of the project through closeout. The objective of this paper is to encourage project teams to take the appropriate time and effort to assess project risks with the goal of providing an organized and practical approach to project risks and opportunities.
RISK-3920 | A Hybrid Quantitative Schedule Risk Analysis using Earned Value Management and Risk Drivers Methods | Dr. Mohammadjavad Arabpour Roghabadi; Dr. Osama El Sayed Moselhi, P.Eng.; Sedat Akkaya; Angus Johnston | 2022 | Infrastructure projects are becoming increasingly complex given governments' demand for building innovative and smart cities. Forecasting a realistic schedule contingency is a major concern for managing this class of projects. Existing scheduling models often run based on subjective data collected from members of project delivery team (PDT) without incorporating historical data of the project. The confidence level of the result heavily relies on the experience of the PDT and their subjective judgment. Accordingly, this paper presents a data-driven quantitative scheduling risk analysis model that employs reported schedule performance data to the project in-hand in combination with a set of schedule risk drivers for forecasting project schedule contingency. It utilizes earned value management (EVM) and risk drivers methods to account for correlation between activities’ duration, which is a drawback of the risk-based EVM methods reported in the literature. A real case example in the transit sector is utilized to compare the performance of the developed model with commercially available scheduling software. The results indicate that the developed model yielded schedule contingency close to that generated by the software, but with considerably less effort and less demand on data preparation and processing.
RISK-3965 | Perceptions and Use of Building Price Data in Australia | Dr. Anthony J. Mills; Dr. Argaw Gurmu; Dr. Citra Ongkowijoyo; Dr.Wenying Yao; Dr. Alexia A. Nalewaik, CCP FAACE; Anthony Lieberman | 2023 | Recently, the Australian Institute of Quantity Surveyors (AIQS) commissioned a study of construction price data published by the Institute. The goal of the study was to gain a deeper comprehension of how the published data was used, and perceptions of its accuracy and value. This building price data has been published periodically by the Institute since the 1970’s, but there was not previously much effort expended to understand how useful the data was to members, and whether it was suitable for their purposes. In order to conduct the research, cost data was gathered from The Built Environment Economist, a quarterly magazine published by the AIQS. The research itself was conducted in stages. A survey of users of the cost data (magazine subscribers) was conducted, the published one-year cost index forecasts were compared to the reliability of other trusted published statistics, and the one-year forecasted data accuracy was checked by building forecast models. The models used were based on commonly used forecast techniques (specifically, vector error correction (VEC) and exponential smoothing (ES)). Based on the study results, the research team identified key benefits and drawbacks of the published cost data, and identified for the AIQS several options for improving the published data product. This research provides insight into the methods used to generate building price forecasts and is useful to individuals involved or interested in generating and improving the usability of published building price information. In particular, the study sought to understand what building price data end-users value most, and how cost engineers perceive the price forecast accuracy. The study also provides a fresh perspective on how building price data providers and their member/customers interact.
RISK-4038 | Lessons Learned from the US Department of State, Bureau of Overseas Buildings Operations, Office of Construction Management on its Enterprise-wide Implementation of Project Risk Management | Sholeh Lee, PE; Benjamin R. Hodel; Justin Jacobsen, PRMP PSP; Michael T. Siburt, PE CCP PRMP PSP | 2023 | Project risk management has for decades been recognized by the US GAO as a project best practice who has urged federal agencies to conduct cost and schedule risk analyses to evaluate, quantify, and mitigate risks that can lead to cost increases and schedule delays. This paper will highlight the efforts at advancement and implementation of project risk management policies and supporting processes within the US Department of State, Bureau of Overseas Buildings Operations (OBO), Office of Construction Management in alignment with this GAO guidance. Initially launched as a pilot program, OBO recognized the value of enterprise-wide implementation of project risk management, expanding use beyond just the largest or most complex projects. OBO is driving a cultural shift within its respective project management structure with the implementation of these project risk management fundamentals, which has and will continue to reap rewards in improved project outcomes. Through lessons learned, this paper will explore the challenges and opportunities of these enterprise-wise efforts, including examining the way in which OBO is achieving team commitment, utilizing champions, establishing a proactive risk management culture, using defined requirements, and offering and updating training for their teams.
RISK-4073 | (Presentation Only) Managing Coefficient of Variation in Monte Carlo Based Cost Models | Stephen Koellner | 2023 | Effective estimators develop risk-adjusted models that account for statistical uncertainty to calculate a range of possible cost outcomes for a project. The coefficient of variation (CV) of a risk-adjusted model is a statistic that normalizes uncertainty to determine if appropriate bounds have been captured in the estimate. The bottom-up application of cost uncertainty requires the use of Monte Carlo simulations. Despite many benefits, this approach is susceptible to underestimation of uncertainty for top-level work breakdown structure (WBS) elements. Failure to understand the causes of this underestimation could prevent realistic generation of bounding estimates. Unreasonable upper bounds for potential costs may present false flags while assessing performance as part of the PDCA cycle of TCM, as reasonable cost growth exceeds variance from the underestimated plan. This topic illustrates how elements such as WBS size, correlation, and uncertainty of lower-level elements can impact top-level spread in a WBS using a derived equation and randomly generated WBSs. The discussion will identify root causes of risk underestimation in Monte Carlo based models along with mitigation steps for addressing the underlying issues. Program management professionals and cost estimators can apply these insights and guidelines to manage cost-growth risks more effectively by more accurately quantifying cost uncertainty to enable data-driven decision making.
RISK-4091 | Reducing Subjectivity of Qualitative Risk Scoring and Analysis | Dr. Ashraf Salem, P.Eng.; Dr. Emad Elwakil, PE CCP | 2023 | Probability, impact, and risk scoring are usually encountered with significant subjectivity during risk identification and qualitative assessment process. This subjectivity is severely reliant on personal bias and level of expertise of the participants in risk workshops. This paper introduces a novel method to reduce such subjectivity using fuzzy-set theory. The developed method accounts for the variation in assessing the probability of occurrence and the potential impacts on the project objectives and interests. The method converts the stakeholders’ linguistic evaluation to a fuzzy number and hence to a crisp number that provides an objective representation of probability, impact, and risk scoring for each identified risk. Finally, results are discussed, and conclusions are drawn highlighting the applications of the developed model and how it can assist owners, contractors and project managers for efficient risk identification, scoring, and analysis process.
RISK-4118 | A Causal Approach to Integrated Risk Analysis Using Time Performance Factors | J. Gerard Boyle, CFCC | 2023 | A survey of current literature pertaining to risk analysis reveals consensus that integration of cost and schedule is essential to reliable assessment of the risk to the time and cost objectives on construction projects. There are, however, major differences of opinion regarding how cost and schedule should be integrated into risk analysis. At one extreme, it is argued that statistical or parametric techniques are superior to CPM schedule analysis. Adherents of a more “traditional” approach do use a CPM schedule, but insist the contractor’s detailed execution schedule is unnecessary. Instead, a summary level schedule is validated by “plenary stakeholders”. Acknowledging that the methods both have advantages and disadvantages, risk analysts are counseled to use two or more methods (a hybrid approach). This paper identifies fundamental flaws in risk theory and practice. A worked example is used to critique the integrated cost and schedule risk analysis method using risk drivers and Monte Carlo (“MC”) CPM simulation. A primary problem is that the analysis is not causal; it doesn’t account for the deterministic connection between output (effect) and input (the causal productivity and resource supply factors). Moreover, assumptions about the connection of labor cost and time are incorrect. As a corrective, new performance formulas and analytical approaches successfully used on major construction programs are introduced. Ideas are proposed for future research and development pursuant to improving the reliability of risk and schedule analysis.
RISK-4119 | (Presentation Only) Quantitative Schedule Risk Analysis For Revivitalization Project at Early Stages | Adalberto Marques da Costa; Rodrigo Maia Francisco da Costa | 2023 | The purpose of this presentation is to present a case study about a quantitative schedule risk analysis applied to revitalization projects focused on early stages, in the Petrobras Exploration & Production Area. A revitalization project, in Petrobras, is defined by the deployment of a new floating production system in replacement of one or more existing production systems, partially reusing subsea equipment and wells. These kinds of megaprojects, especially in FEL 2, present some unusual challenges: even though more mature reservoir information is available compared to a greenfield project, there are a lot of wells (25 to 80) involved and some technical alternatives available to apply. In this stage at Petrobras, it is required to run quantitative schedule risk analysis in two separate times: (1) to support the procurement strategy and (2) to get a predictability schedule at the decision gate of the conceptual design. The authors want to share these findings, the internal process, and issues to achieve the outcomes.
RISK-4124 | Risk Management Lessons Learned | Christopher P. Caddell, PE CCP DRMP FAACE | 2023 | Many organizations have implemented formal risk management practices at either the individual project level or as a part of management of an overall capital program. However, often those organizations are not seeing the anticipated benefit from implementing those practices. They continue to have projects fail by going significantly over budget, experiencing pronounced delays, or suffering major disputes between parties. Having reviewed a large number of projects in these programs over the past twenty years, the author has identified many lessons learned that have impacted the value an organization receives from implementing risk management. The lessons learned cover all facets of a risk management program, including risk management planning, identification, qualitative and quantitative assessments, response, and monitoring. The issues include mistakes in implementation, tool utilization, poor understanding, lack of collaboration, and lack of commitment. The author has witnessed issues in each of these areas that reduce the effectiveness of the risk management program. By highlighting these issues and how to address them, other organizations can benefit from these lessons learned and maximize the value of a strong risk management program.
RISK-4144 | A Risk-Based Approach to Construction Management | Chloe E. Edwards; Yasaman Shahtaheri | 2023 | Risk management plays a fundamental role in project controls and delivery. The purpose of incorporating risk management into project management practices is to identify and address uncertainties related to key project-related activities. The uncertainties, known as risk events, can relate to project deliverables that are quantifiable and are often measured by impact to project schedule, cost, or environmental impact. Risk management should be incorporated as an iterative practice throughout the planning, execution, and commissioning phases of a project. This paper specifically examines how risk management contributes to effective project controls and delivery through a case study of a transportation project. The case study covers a 12-kilometer heavy rail design and construction project through multiple municipalities and natural environment. A risk-based approach was implemented to evaluate the risk-based contingency for construction and design costs, evaluate project duration, and prepare and implement mitigation strategies to increase the likelihood of project success.
RISK-4240 | Case Study: Use of the Hybrid Parametric and Expected Value QRA Method on the Keeyask Hydropower Megaproject | John K. Hollmann, PE CCP CEP DRMP FAACE Hon. Life; Raminder S. Bali, PEng | 2024 | Keeyask is a new 695-megawatt hydroelectric generating station on the Nelson River in Canada’s Manitoba province developed as a collaborative effort between Manitoba Hydro (MH) and four First Nations – Tataskweyak Cree Nation and War Lake First Nation (operating as the Cree Nation Partners), York Factory First Nation, and Fox Lake Cree Nation – working together as the Keeyask Hydropower Limited Partnership (KHLP). MH managed the construction and operates Keeyask, which has been fully online since 2022. The primary Keeyask project scope included earth-filled dams and earthen dikes, a powerhouse with seven turbine units, and a seven-bay spillway. In the early stages of Keeyask’s stage-gate process, quantitative risk analysis (QRA) was performed using range estimation. In 2013, prior to the start of construction, Keeyask switched to using cost and schedule QRA applying the hybrid parametric and expected value (P+EV) method along with analyses of specific management reserves and a tipping point (non-linearity) assessment (AACE Recommended Practice 113R-20 covers the P+EV method). This case study reviews the use of the P+EV method on a megaproject during execution. P+EV has advantages for early stages; however, Keeyask applied it during construction. Identified, but under-appreciated, systemic fragility challenges led to non-linear behavior; total cost increased from $6.5 to $8.2 billion Canadian dollars and the first unit in-service milestone slipped 15 months from November 2019 to February 2021. This is not a story of flawless prediction, but is a practical lesson learned guide on applying P+EV on a project in which the nature of the risk and analysis teeters on the brink of statistical disorder. Learnings and recommendations are provided.
RISK-4247 | Defining a Lognormal Distribution Using 3-Point Entry: The J-QPD Distribution | John K. Hollmann, PE CCP CEP DRMP FAACE Hon. Life; J. Eric Bickel | 2024 | Practical quantitative risk analysis (QRA) methods using Monte Carlo simulation (MCS) for project contingency determination often rely on 3-point distributions. In a typical project QRA workshop, 3-points (e.g., low, most likely, high) have proven to be the extent of the cost and schedule risk impact range input that most analysts can expect to obtain from project teams. In AACE RP 66R-11, there are only two practical probability distribution functions (PDFs) defined by 3-points: Triangular and PERT. Neither is an ideal representation of naturally occurring cost growth and schedule slip data distributions. Industry research suggests that the Lognormal distribution is a more realistic fit for large projects based on actual project cost and schedule variability. Risk analysts, attempting to be realistic, often resort to PDF variation (e.g., trigen) and/or attempt to push teams toward the analyst’s opinion of acceptable 3-point input. This manipulation can raise stakeholder suspicions about the reliability of MCS, and rightfully so. What is needed is a lognormally shaped PDF that can be defined with 3-point input. Recently, researchers at the University of Texas developed a distribution system called the Johnson quantile-parameterized distribution (J-QPD) that is able to match the shapes of common distributions, including lognormal with 3-point input. This paper will review the typical QRA PDF use context, describe the J-QPD distribution and its use criteria, and provide practical examples of its application in an MCS-based QRA method. The authors will propose an RP 66R-11 update and encourage MCS software vendors to include the J-QPD as a distribution choice in their products.
RISK-4307 | Treading Cautiously: Risk Management in the Leapfrogging of Offshore Wind Turbine Technologies | John Coker; Emily J. Byrd | 2024 | As the global commitment to sustainable energy and green tech intensifies, offshore wind technology is experiencing significant advancements. These developments, characterized by larger blades and turbines, promise heightened efficiency but also introduce a range of challenges in transportation and installation. This paper delves into the complexities of these advancements, identifying and analyzing the risks they pose—from logistical and regulatory hurdles to financial repercussions. It presents a comprehensive risk management framework, informed by expert insights, designed to address these challenges effectively. The framework provides stakeholders with a structured approach to managing risks associated with the deployment of advanced transport methodologies in the offshore wind turbine sector. By emphasizing proactive risk management, the paper aims to equip stakeholders with the necessary tools to navigate this rapidly evolving landscape, thereby contributing to the sustainable growth of the offshore wind industry. This work stands as an essential guide for industry professionals, highlighting the critical role of strategic risk management in adapting to and capitalizing on technological innovations.
RISK-4330 | Navigating Risk Management Challenges in Progressive Environments: Case of Progressive Design Build Contract Delivery Models | Roozbeh Panahi; Katia Rizkallah; Kyle Mawhinney; Sara Martino | 2024 | Progressive contract delivery models have gained prominence in mega-construction projects, particularly in Canada, owing to distinct advantages such as increased market engagement, refined project definition, early risk mitigation, and project acceleration. A robust risk management practice can play a crucial role in the success of these models. The convergence of all relevant parties at a single platform during the iterative progression of project details during the development/design phase offers valuable insights into necessary changes concerning various risks and corresponding risk management strategies, contributing to the overall success of the project along with a well-defined schedule and cost estimate for the implementation/construction phase. Nevertheless, risk management may face challenges during the development/design phase that can minimize the benefits of progressive models. These challenges can emerge as a result of inadequate information, a dynamic and rapid-paced environment, diverse risk cultures, and limited expertise, among other factors. This article's primary objective is to examine risk management challenges in the context of the Progressive Design Build (PDB) model, a variant of progressive contract delivery during the development phase. In doing so, the article benefited from in-depth analysis of the risk management steps, direct contribution of the team and unstructured interviews with project controls and technical teams involved in relevant projects.
RISK-4345 | (Presentation Only) Review of Risk/Reward Sharing Mechanisms in Collaborative-Based Projects | Dr. Moe Roghabadi; Camelia Bucur; Dr. Farzaneh Golkhoo; Sohiel M. Hassan | 2024 | Collaborative Contracting Models have been receiving worldwide attention, especially in the UK and Australia, with increasingly more countries exploring its use. It is a relatively new delivery strategy in Canada where owner and all non-owner participants (NOPs) work together with integrity and making best-for-project mindset decisions. Risk/reward sharing is an important concept to provide incentive for project participants to enhance the project performance and achieve a win-win scenario for all those involved. There are multiple approaches from the literature that explored how the risk/reward sharing ratio can be optimized to incentivize parties’ risk solving efforts. As such, this paper summarizes previous work relating to this topic and compares 2 specific approaches in more detail to serve as a guide and to initiate further future discussion on improved methodology for risk/reward sharing ratio optimization. Key aspects influencing the risk/reward sharing mechanism are defined and serve as the foundation for the comparison. These principal aspects include participants’ risk attitudes, cooperative behavior and the stochastic nature of risks, customized risk perception based on risk criteria, and optimization strategies. A numerical case example adapted from the literature is also used to present the relevant methodology and outputs.
RISK-4356 | Enhancing Decision-Making Process through Probabilistic Schedule Analysis Across the Project Lifecycle | Abbas Shakourifar, PSP; Dr. David T. Hulett, FAACE; Keith D. Hornbacher; Steve Uhl | 2024 | This paper advocates for a re-imagining of how logic networked schedule risk analysis (SRA) can add value to projects. In the authors’ view, SRA should be considered a critical decision-support tool, leveraged to help projects add value by informing executives about risk/rewards trade-offs on many decisions, small and large, throughout the project life cycle. This approach contrasts with what one frequently observes in practice: SRA used primarily as a highly detailed quantification and assurance tool at the time of final investment decision (FID), to get projects approved and perhaps highlight some risk treatment priorities. These applications are valuable, but they underutilize the potential of SRA for mid-phase incremental decision making while scope and plans are developed, and value is optimized. This paper offers actionable insights as to how to apply SRA to support incremental decisions. It properly views SRA as supporting asset and project optimization, value and change management: foundational elements of Cost Engineering and Total Cost Management (TCM). A case example is presented, illustrating how one company used SRA to help navigate critical non-FID scope development and planning decisions during Class 4, 3, 2 and execution phase. Highlighted are the many types of decisions that may benefit from the approach, as well as practical tips to use SRA in a more fit-for-purpose manner. In summary, SRA emerges as a dynamic and frequently applied decision-support tool that can add value in new ways during multiple phases in the project life cycle.
RISK-4367 | Challenges Aggregating Multiple, Interdependent Projects into an Integrated Program-Schedule Quantitative Risk Analysis | Dr. David T. Hulett, FAACE; Ian Bailey; Lorrie B. Tietze | 2024 | Some complex programs are structured so that many separately managed projects must interact with each other to produce the final integrated deliverable. Constituent projects typically have large and detailed schedules and are often assigned to various entities under the same umbrella organization, company or government agency. The constituent projects are specialized entities, focusing on design, fabrication of various components, integration and/or production of multiple units for the ultimate customer. Each entity has their own deliverables that are used by another entity for their work, making downstream work dependent upon someone else’s upstream work, and so on. Each individual entities’ efforts are integrated in a development program to deliver the first production unit (FPU) of the final system to the customer (e.g., a major program milestone). The following steps describe the sequences and challenges faced by complex programs: • Each entity’s project, within the integrated program has its own level of uncertainty and set of entity-level risk events. Due to the interdependencies between projects, a delay experienced by one entity, the “giver” of a deliverable (e.g., design, test results, OK to proceed, etc.), is transmitted to another entity, the “receiver” of that deliverable, the delay rippling through the rest of the entire program’s integrated schedule. • There are risk events that affect only one of the entities and other risk events that affect several of the entities at once. The cumulative effect of a risk event impacting multiple entities could be much larger to the overall program success than the impact of any single-entity risks. • A quantitative risk analysis, for a giver entity, can forecast a probabilistic delay, to the receiver entity, for the needed deliverable at a higher confidence level. If the receiver is informed about the delay in a timely manner, it can be included in the receiver’s risk-informed plans. • It is not sufficient to just push the new commitment date changes from one entity to another for each giver-receiver combination. The work and schedule are not strictly sequential, having many parallel paths and feedback loops. A design will mature into a finished project eventually, but there are instances of the receiver entity returning the product (e.g., design, component, sub-assembly) to the giver for further re-work before it resumes its way toward the final integrated product. The quantitative analysis update process must be coordinated so that all the hand-offs (i.e., deliveries and receipts) are shared at the same time. The simultaneous sharing enables viewing of the knock-on or ripple effect when a delivery slips early in the schedule causing multiple delays later in the schedule. • Once the coordinated hand-off commitment dates are updated, the receiver entities need to incorporate the giver’s delays in their own planning. The knock-on effects of the giver’s delay on the receivers’ plans need to be represented so the receivers’ output (e.g., maybe to other receivers such as the fabricating entities) will correctly reflect the complete set of compounded delays. This integration appropriately represents the work of, and interconnections between the entities, and is used to conduct a program-level quantitative risk analysis. After trying several approaches NNSA’s current strategy develops a representative program schedule that includes the top-level projects’ deliverables, and giver/receiver hand-offs between entities. The key challenges with this strategy are maintaining the representative integrated program schedule, ensuring sufficient input data quality and consistent representation of the entities’ individual schedules and cross-entity dependencies. Once the integrated program schedule is created, the potential consequence of risks and uncertainties to the program final delivery to the customer can be determined. Additionally, program level risks can be analyzed at a program level vs. having individual entities analyzing only their piece of the overall impact. Risks can be identified, determined if they are entity risks vs. program risks, evaluated, and understood appropriately so that plans for mitigation can be completed as early as possible. With early risk evaluation, other options can be considered and evaluated, including early planning/structural program changes, scope reduction, putting low-priority scope toward the punch list or carefully putting non-dependent activities in parallel rather than in series (and effective backup plans) at the start of a major program. The integrated program schedule, informed by the individual entity quantitative risk analysis results, then becomes the basis for analyzing and optimizing the program. The focus must be on optimizing the program vs. optimizing any individual entity’s project. Since the risks that impact one entity are accounted for in their individual risk analysis, the program risk analysis prioritizes the risks that affect one entity, multiple entities, or the entire program. Program risk mitigations can then address the risks that are the biggest threat to the final program’s success in delivering the final product to the customer. This paper uses a small representative model of the National Nuclear Security Administration (NNSA) modernization program to explore the issues above and address the following risk analysis activities: • Building individual program entities’ schedule so they can be integrated. • Linking the output of the sender entities to the inputs of the receiver entities. • Evaluate integrated program schedules and quantitative results using alternative risk evaluation strategies. • Risk impact prioritization for focused, cost-effective mitigation across all entities to optimize the spend for mitigation and the overall program.
RISK-4401 | Assessing Proposed Risk Mitigation Actions Using Mitigation Scoring | Waylon T. Whitehead; Dr. David T. Hulett, FAACE | 2024 | Much has been written about best practice project risk analysis. But what happens after the risk analysis concludes that the pre-mitigated project is not going to be successful? Often, the risk analyst is asked to improve the project’s funding prospects by assessing the project using post-mitigated risks. Strategic and tactical improvements in risk management are necessary to improve mitigation outcomes. Risks can be prioritized as an output of the quantitative risk analysis. Then, risk mitigation workshops can be held to see if the high-priority risks can be mitigated effectively and economically by adopting new mitigation actions focused on the specific risks. But do the mitigations developed truly have a chance of changing the project’s prospects? To be meaningful, a risk mitigation action must be new, not a continuation of a previous or normal practice. “Continuing to hold weekly meetings with subcontractors” does not qualify. Mitigations for the high-priority risks should be precise and tactical, with an assessment of required support such as funding or hiring. It should cover what will change and specifically how the change will be implemented. Alignment should be reached on the mitigations between all main stakeholders - owner, contractors, subcontractors, commissioning agents, and regulators. This paper presents a 6-level scale and associated concepts that can be used to evaluate the quality and potential effectiveness of proposed mitigations. The focus is on relevance to the risks, practicality of the action within the context of the project, clarity of definition of actions, and stakeholder commitment to the resulting plan. The Whitehead-Hulett Mitigation Assessment Score (MAS)TM is introduced and its use is described with actual project examples. To warrant any potential credit (represented as a lower probability of occurring, less impact if it were to occur, or both) given in post-mitigated quantitative modeling, the mitigation should have a MAS of 3 or higher, with 4 or 5 being preferred. Achieving those MAS values indicates that the mitigations are thought through well enough to be taken seriously. The MAS scale also directs project teams on how to improve their mitigation strategies. This paper introduces and describes: 1. Importance of risk description metalanguage to developing effective risk mitigations. 2. Importance of mitigation element maturity to create real reductions in risk profile of the project. 3. Proposed 6-level scale to assess risk mitigation maturity. 4. Recommendation to avoid using full set of post-mitigation analysis estimates to set contingency values. 5. Recommendation to use alternate approach to assessing post-mitigation only after MAS of threshold value or higher is achieved, with analysis being iterated as solutions are developed. 6. Reasoning for using alternate approach to accepting post-mitigation estimates only after sufficient maturity is reached.
RISK-4435 | Practical Implementation of AI-Based Risk Analysis on Construction Megaprojects | Rhys Phillips; Dev Amratia; Carlos Ledezma; Richard Bendall-Jones; Vahan Hovhannisyan; Leonie Anna Mueck | 2024 | Recently, AI-schedule risk analysis (AI-SRA) has emerged as a groundbreaking approach to construction project risk management. [1,2] Unlike traditional quantitative schedule risk analysis (QSRA),[3] AI-SRA leverages machine learning models, trained on extensive historical schedule data, to directly predict activity durations distributions based on data embedded in the schedule. As previously shown, AI-SRA surpasses traditional QSRA in both the accuracy of end-date forecasts and activity duration predictions. [4,5] Despite its proven effectiveness, practical implementations of AI-SRA within project organizations have so far been scarce and the practicalities of rolling out this new process are unstudied. Here, a comprehensive study of how to implement AI-SRA successfully on megaprojects is presented. AI-SRA roll-out on five projects across different sizes and sectors shows that, generally, three challenges need to be overcome: Lack of trust in AI models; the unintuitive nature of AI-SRA results; and AI-SRA differing from tried and tested processes. These challenges can be overcome by clear steps towards understanding AI, visualizations to aid comprehension of the results, and demonstrations of equivalence of AI-SRA to traditional processes. As a case study, the specific application of these principles on a major UK rail project using AI-SRA is discussed.
RISK-4481 | Quantitative Schedule Risk Analysis for Upstream Strategic Plan | Adalberto Marques da Costa; Fabio Martins de Rezende; Raphael Seixas dos Santos; Rodrigo Maia Francisco da Costa | 2025 | The objective of this work is to conduct a quantitative schedule risk analysis (QSRA) on several Subsea Tieback Projects from a major oil company. Previously, the company relied on a deterministic start-up production date as an input for key performance indicators in the Annual Strategic Plan. To enhance the predictability of this plan, the authors initiated QSRA for the major projects in the company’s portfolio. As a result, the company experienced several outcomes and benefits. Firstly, the physical schedule became more robust, ensuring a more reliable timeline for project completion. Secondly, the authors identified the activities that impact project start-ups most, enabling prioritization and allocation of resources more effectively. Additionally, the predictability index of project planning, in terms of schedule and net present value, improved significantly. Furthermore, this analysis provided clear visibility into the portfolio's project contingency, allowing for better risk management. Lastly, it contributed to cultivating a stronger project-planning culture within the company. This work highlights the value of adopting a realistic approach to identifying project risks and uncertainties. Moving forward, in the next cycles, projects should focus on implementing action plans to address the root causes of the main risks identified.
RISK-4494 | Statistical PERT™ Analysis Applied to Contingency and Comparative Results with Data for Mining and Energy Projects | Victoria Tillous; Murray Pearson, PEng; Katherine Wong-Cameron, PEng | 2025 | Historically the construction industry has experienced a poor record of delivering projects within their sanctioned budgets. Such capital cost estimate (CAPEX) overruns are well documented in media and industry publications. Large projects often run 15% to 20% over budget, risking approximately $1.5 billion US of capital each year through 2030 [4, p4]. To improve CAPEX ranging analysis, the authors propose creating a model for Statistical PERT® analysis to be applied during prefeasibility studies. The historical data used to support the research is sourced from published feasibility studies and publicly released capital costs for completed projects. The projects of interest were completed between 1997 – 2024, where project elements were analyzed to determine the distribution representative for mining and energy projects. A statistically significant sample of 50 projects were selected to test the Statistical PERT® analysis by comparing the model simulation to final outcomes in two case studies. The research allowed development of realistic risk profiles compared to assuming a normal distribution of risk (i.e. traditional Monte Carlo analysis), to improve insight of elements with dominant interdependencies. The proposed approach is a cost-effective early assessment tool that can be used prior to investing in a qualitative risk analysis (QRA). The results also highlight areas of influence to be considered in conjunction with early execution planning to provide transparency on potential causes and measures to mitigate CAPEX overruns.
RISK-4514 | Comparison of Quantitative Risk Methodologies for Program and Portfolio Risk Analysis | Rachel A. Fleming | 2025 | This paper examines and compares various quantitative risk analysis methodologies within program and portfolio environments. The study evaluates methodologies and combinations of expert judgment, predetermined guidelines, parametric, simulation analysis (expected value and critical path method), analytics (artificial intelligence and machine learning), and reference class forecasting to analyze their applicability. The paper highlights the strengths and limitations of each approach in terms of suitability for application to program and portfolio analyses. Through a review of existing literature, including relevant AACE recommended practices (RP), the paper proposes evaluation criteria for selecting and integrating these methodologies to enhance risk analysis in support of better decision-making. The findings aim to guide project managers and risk professionals in choosing the most suitable quantitative methods for analyzing risk in program and portfolio settings, contributing to more resilient and successful program outcomes. This will also help frame potential future RP development plans.
RISK-4522 | The Risks in Project Risk Management: An Assessment Using a Fault Tree Analysis Framework | Justin Jacobsen, PRMP PSP; Christopher J. Payne, CFCC PSP | 2025 | Project risk management in construction involves systematic processes to identify, assess, treat, and monitor risks that could impact project objectives. This process is inherently scalable, allowing it to be tailored to the size and complexity of projects—from small renovation projects to large infrastructure undertakings. Formal risk management documentation provides a structured and transparent approach, enhancing accountability and enabling thorough analysis. Through this process, projects should realize a much higher likelihood of success in achieving project objectives and reduced exposure to costly budget and schedule overruns. From a project owner’s perspective, there is occasional hesitation in implementing formal risk management due to the perception that formally addressing risk only brings additional risk to the project. Whether this stems from the ineffectiveness of risk treatments, inefficient use of time for busy project staff, or the perception that added focus on project complexities and uncertainties will increase the likelihood of a dispute or adverse claim, this lack of support compromises the benefits offered by using a formal risk management approach. This paper intends to use fault tree analysis to identify these potential compromises of the project risk management system and further explore types of failure using failure mode effects analysis. These failure points will be assessed qualitatively to determine their impact on the project objectives. After structuring the problem this way, the paper will describe a hypothetical case study to further extend the analysis, discuss potential outcomes, and describe mitigation approaches. The analysis identifies five key themes or categories of failure that could counteract the effectiveness of a risk management system and suggests mitigation measures for each. Though formal risk management is not without its own risks, the authors believe the benefits will outweigh any potential inherent exposure. Acknowledging potential failures and taking care to implement mitigation measures should lead to a robust system that is able to provide the intended benefits to project outcomes.
RISK-4572 | Fuzzy Set-Based Analysis of Productivity Variations | Dr. Ashraf Salem, PEng; Elsayed Salem; Dr. Emad Elwakil, PE CCP | 2025 | Throughout all project stages, including planning, implementation, and operation, the dependability and efficiency of an analytical tool are vital. Realistic operational designs and strategic planning can be developed through a thorough assessment of productivity and project performance; early identification of inefficiencies and system bottlenecks helps guarantee the timely implementation of corrective actions in a methodical and prioritized way. This paper offers a methodical approach to performance assessment using a model based on fuzzy set theory to evaluate deviations between actual and intended productivity. The developed assessment model consists of two tiers of assessment and analysis modules. A productivity-monitoring technique based on low-optimum-high (LOH) fuzzy sets is presented in the first module. These three states:low, optimal, and high. These states are used to assess productivity. Each stage's upper and lower bounds vary depending on the organization or project management. Therefore, each organization can estimate each fuzzy attribute's lower and upper bounds (e.g., Low) based on their experience. The second module provides early warning decision support initiated based on the productivity assessment module. This study fosters multidimensional construction, mining, and transportation project management applications. A case study is represented to demonstrate the applicability of the developed model. The results obtained highlight the accuracy of the developed model in recognizing the variations in productivity.
RISK-4575 | Schedule Risk Prioritization in Monte Carlo Simulation | Rasoul Abdolmohammadi, CCP | 2025 | Among the various methods for conducting schedule risk analysis in projects, Monte Carlo simulation of schedule networks is widely considered the preferred approach. However, one of the primary challenges faced by risk analysts after running a Monte Carlo simulation is the prioritization of risks, which is typically based on either the correlation of risks or their impact on the project. To calculate the schedule impact of risks, this paper critically examines the method proposed in AACE Recommended Practice 57R-09 [1], which is widely regarded as one of the best approaches to date. The paper highlights key shortcomings of this method, including its misalignment with real-world scenarios and inconsistencies in the concept of confidence levels. To address these issues, the paper introduces two new methods that focus on the sequence of risk removal and the development of confidence levels. To establish a mathematical framework for prioritizing risks, this paper explores the concept of correlation and introduces the notions of risk elasticity and cruciality to enhance the accuracy of the results. Currently, risk importance is assessed using correlation, the prevailing method in the industry. However, correlation alone does not account for a risk’s criticality-defined as the sensitivity of the total project duration to the duration of a specific risk. To address this limitation, this paper introduces the concept of risk elasticity. Furthermore, to incorporate both importance and criticality, risk cruciality is proposed as a combined measure of risk correlation and risk elasticity. The importance of risks is currently calculated using the Correlation that is the current privilege method in industry. Through Correlation, the criticality of risk is not calculated. The sensitivity of total project duration to the duration of a risk can be referred to as risk criticality. The elasticity concept is introduced in this paper as a response to this matter. And to have both importance and criticality together, the risk cruciality is introduced by combining risk correlation and risk elasticity. The discussions and conclusions presented in this paper highlight that combining correlation with elasticity produces more reliable results than using correlation alone. Furthermore, the proposed methods for calculating schedule risk impact effectively overcome the limitations of existing approaches.
RISK-4593 | Calculating Project Risks Like Financial Market Pros | Austin M. Spina | 2025 | In an effort to reduce the cognitive human biases that influence the underestimation of project risks, this paper describes and implements a process to account for duration based risk on a project. This process algorithmically increases the amount of risk contingency on a project. The paper presents a simplified version of the Black-Scholes stock option model for application in the field of project risk management. The simplified equation calculates a factor to adjust individual project risks to account for their time of risk exposure (TORE). The TORE is defined as the duration of time where a risk could occur. The paper then explores various applications of the TORE factor in existing project risk management practices.
RISK-4615 | Simulation-Based Risk Allocation in Collaborative-Based Projects | MennatAllah Hammam; Sohiel Hassan; Dr. Moe Roghabadi; Dr. Osama Moselhi, PEng FAACE | 2025 | Effective risk management, particularly risk allocation, is essential for the successful delivery of collaborative-based projects. While there is extensive literature on risk assessment and quantification, research on dynamic risk allocation methods in collaborative environments remains limited. This paper introduces a dynamic framework for probabilistic risk allocation that supports fairness and efficiency for determining risk ownership by continuously adapting to project conditions, stakeholder capabilities, and behavioral dynamics. The proposed framework introduces a risk evaluation process for different project phases, enabling the end user to make data-driven decision making for determining the best suited party for managing risks. Rooted in collaborative project delivery systems, this approach ensures that risk allocation remains flexible, responsive, and aligned with stakeholder capabilities. By integrating findings from literature, case studies, and lessons learned, the framework provides a structured simulation-based methodology for enhancing risk allocation by reducing subjectivity and bias as the project progresses. An illustrative numerical example is presented to showcase the practical application of the framework.
RISK-4616 | Checklist for Integrated QRA Modeling | J. Gustavo Vinueza | 2025 | Effective risk management is essential for project success but can be complex, especially for beginners. This paper simplifies integrated cost and schedule risk management (ICSRA) through a practical, accessible checklist. Using a representative case study, it demonstrates how uncertainty and risk events affect project timelines and budgets, helping practitioners apply QRA with confidence across industries and project types. The focus will be on creating an intuitive checklist that participants can apply in any industry, project size, or level of complexity. The goal is to help practitioners navigate risk management and equip them with the tools they need to effectively manage uncertainty in their projects. The paper explains how practitioners can connect theoretical concepts to practical applications, making risk management not just a checkbox activity but an integral part of successful project planning and execution. This checklist will serve as a foundational tool that helps participants manage uncertainty effectively, providing them with the confidence to approach any project with a structured and proactive risk management mindset, using a versatile, easy-to-use framework. This session is ideal for project managers and professionals at the start of their risk management journey, looking to gain a practical, hands-on understanding of managing uncertainty with confidence. Whether working in construction, technology, finance, or any other field, the principles discussed in this session will adapt to specific context, helping take immediate, actionable steps toward better risk management.
RISK-4672 | Premeditatio Malorum: A Stoic Approach to High-Impact, Low-Probability Risk Management in Major Projects | Dr. Manjula Dissanayake, CCP | 2025 | Major capital project execution is plagued with cost and schedule overruns across the globe. Substantial efforts are invested in planning and preparing projects, including the identification and mitigation of risks and uncertainties through qualitative and quantitative risk models. Despite these efforts, residual uncertainties remain and are often a major contributor to overruns. These include both ‘known unknowns” and ‘unknown unknowns” that are difficult to incorporate into typical risk models and project controls approaches. These uncertainties tend to be high-impact, low-probability (HILP) events. They are typically overlooked or impact is underestimated and not adequately prepared for. This paper presents an approach to HILP risk management using a timeless Stoic practice called premeditatio malorum, a Latin phrase meaning "the premeditation of evils," to plan and prepare for HILP events to improve predictability.