## Conference Series #08, Vol. 1
ID | Title | Authors | Year | Description
CDR-0815 | Forensic Schedule Analysis - Chapter 2: Delay Analysis on Non-CPM Scheduled Projects | James G. Zack, Jr. CFCC; Steven A. Collins | 2012 | AACE International Recommended Practice 29R-03 – Forensic Schedule Analysis, provides detailed insight in how CPM based schedule delay analysis should be performed. This RP provides thorough and detailed protocols for each of the nine methodologies identified. However, industry surveys from around the globe indicate that a substantial portion of construction projects do not employ critical path method scheduling techniques. Other industry studies indicate that a large percentage of projects complete later than planned. Therefore, it can only be concluded that there are a large number of delays and delay claims on projects that do not use CPM schedules. RP 29R-03 offers no guidance concerning the performance of schedule delay analysis if there are no CPM schedules on the project. This paper presents recommendations on how schedule delay analysis can be performed on projects using nine different non-CPM scheduling techniques. The paper also discusses the five types of constraints present on most, if not all, construction projects and how these constraints must be used in non-CPM schedule delay analysis. The goal of this paper is to initiate Chapter 2 of RP 29R-03 – Forensic Schedule Analysis on Projects with No CPM Schedules.
CDR-0842 | Multi-Primes and Multiple Critical Paths | John C. Livengood, CFCC PSP | 2012 | Numerous states throughout the country require or permit governmental entities to perform major construction through the use of multiple prime contractors. These multi-prime contract laws that usually include a general contractor and at least three mechanical, electrical and plumbing (MEP) contractors, were intended to reduce costs to the owner through greater competition and reduced redundant overheads. While there is evidence that the intended purpose succeeds –– that success only follows from a vigorous management system that actively coordinates work between the multi-primes, either through additional owner staff or paid consultants. Unfortunately, an all-too-common result of this delivery system, when the management system misfires, is the development of separate CPM schedules for each prime contractor, with critical path delays along each schedule, which leads to schedule chaos. This paper will discuss how forensic schedule analysis should approach, identify, dissect, and quantify delays among multi-primes as the parties prepare for litigation.
CDR-0850 | A Model for Construction Delays Claims Assessment | Sasan Golnaraghi; Sabah Alkass, P.Eng. | 2012 | Disputes in the construction industry originate from delays. These delays affect project parties, the contractor and the owner. Loss of either anticipated revenue or opportunity cost and time overrun, on the owner’s side, and increased overhead cost, escalation cost and liquidated damages, on the contractor’s side, are the main impacts of delays. Preparing delay claims is a time and resource consuming process. Facilitating this process will benefit both project parties. This paper presents a new systematic delay analysis technique to assist in the evaluation of concurrent delays, while considering the critical path of the project. This technique allocates delays among project parties. An expert system is designed to classify different types of delays, as well as to offer recommendations on delays or delaying events. The expert system and the proposed delay analysis technique are integrated with scheduling software. Likewise, a costs computing feature enhances the capability of the system and assists the analyst to reduce the time and cost associated with delay claim preparation. This paper discusses the new delay analysis technique.
CDR-0867 | Estimating Escalation Experienced During Project Delay - A Case Study | William E. Kraus, PE CCE | 2012 | Faced with a proposal for escalation costs when a contractor was delayed in completing the latter phases of a project, estimators needed to benchmark the extent to which construction costs had changed from the original substantial completion date to the anticipated revised substantial completion date. The contractor’s proposal, which consisted of a 4 percent increase across-the-board, at first seemed reasonable, even though the proposal also contained remobilization costs that were clearly not. Estimators developed a scheme by which the extent to which costs had escalated was estimated via two different methods – one, by comparing bid costs by the contractor on two individual projects it had bid at the airport in the approximate timeframe of the delay, and a second, by sampling costs from the airports cost database appropriate to the delayed project over the same timeframe. The two different methods yielded similar results and the owner offered a compromise settlement to the contractor. At the time of completion of this paper, the contractor is contemplating the offered settlement.
CDR-0870 | Forensic Schedule Analysis: Example Implementations, Part 3 | Mark C. Sanders, PE CCE CFCC PSP | 2012 | This is the final installment in a series of papers presenting example forensic schedule analyses performed according to the Method Implementation Protocols outlined in AACE International’s Recommended Practice 29R-03. This paper presents the remaining analysis methods—MIPs 3.4, 3.5, 3.6, and 3.9. Each of these techniques is a variation on one of the techniques previously presented. This paper focuses on comparisons between the techniques and the reasons behind the different results found in each analysis. Finally, recommendations are provided for the continued development of example analyses, the continued refinement of analysis techniques, and the development of industry consensus in the area of objective forensic schedule analysis.
CDR-0876 | When's the Measured Mile, Not the Measured Mile? | Mark F. Nagata, PSP; Elizabeth Bradford | 2012 | Whenever the term “measured mile” is used to describe a productivity analysis, the reader’s first impression is that the results of that analysis must be reliable. The method compares the contractor’s achieved productivity during impacted and un-impacted periods to calculate its inefficiency resulting from impact, using resources expressed in terms of a measurable quantity, typically resources performed (quantity of work) over resources expended (labor hours), to provide an inefficiency factor. However, the “measured mile” analysis has been used to measure productivity using variables other than resources performed and resources expended, often providing less favorable or unreliable results. Some analysts merely compare the contractor’s data in two separate time periods, and use information other than quantity of work performed and labor hours expended to complete the work, like percent of work complete, actual costs, or a variation of both that do not always provide a reliable measure of productivity. The intent of this paper is to identify different methods used to calculate the contractor’s productivity and the weaknesses of those approaches.
CDR-0923 | Recommended Contractual Methods for Resolving Delay Events Prospectively or Retrospectively | Patrick M. Kelly, PE PSP | 2012 | The reality of construction projects is that the oft-mandated methodology for granting a contract time extension is ignored during the press of work. This can result in a significant change in the risk allocation between the parties. The traditional risk allocation model requires performing a prospective time impact analysis (TIA), with agreements on time and money prior to corrective work commencing. Yet, when the work is performed before negotiation, the risk allocation has shifted significantly. This paper makes recommendations for two contractual paths for resolution of changes with potential time impacts, to balance risk and responsibility for cost control. The first method, occurring prior to the start of corrective work, uses a prospective TIA to determine entitlement to time, and bilateral negotiation to manage costs. The second method occurs immediately upon completion of corrective work, tracks costs through stringent time and material cost accounting, and determines time through a contemporaneous period analysis. Having two methods for resolution gives project managers additional tools to resolve time-related issues early and prior to contract completion, minimizing potential disputes.
CDR-0948 | Using the Measured Mile to Increase Calculated Delay Quantum | Glen R. Palmer, CFCC PSP; Jeffery L. Ottesen, PE CFCC PSP | 2012 | Traditionally, productivity analyses and delay analyses have been treated separately as two different methodologies and have usually been prepared as separate work products. In reality, however, both analyses address productivity issues. A delay analysis can be used, in part, as a measure of the inefficient use of project time. A productivity analysis measures the inefficient use of project resources. This paper will attempt to draw correlations between these two types of analyses and show a conceptual methodology that can be used to increase the calculated delay quantum of a delay analysis by using the results of a “measured mile” analysis. Using this methodology it is possible to increase the number of days for which time driven cost damages are attributable to another party.
CDR-0963 | Case Study of a CM’s QA/QC Performance Using the TCM Framework | William M. Hart, PE CFCC PSP | 2012 | This case study examines the role of the construction manager (CM) in quality assurance/quality control (QA/QC) in the framework of total cost management (TCM), as described by AACE International. How the typical CM-agent may succeed or fail is seen by means of a case study – the expert analysis of a heavy civil/transportation project. This paper explains how the CM’s QA/QC obligations are derived from both contractual requirements, as well as from industry performance standards. It also demonstrates how to evaluate a CM’s QA/QC performance based on the concept of “PDCA” (plan, do, check, and assess), on which the TCM process model is based. The case study reveals that the role of the CM in construction quality does not end with simply defining an effective QA/QC strategy in the project management plan (PMP). The CM must provide a complete plan that must be fully implemented, evaluated for effectiveness, and adjusted on a continual basis to assure project quality.
CDR-0966 | Creating Mid-Period Schedules in Window Analysis Using Primavera Version 6 | Patrick M. Kelly, PE PSP | 2012 | Windows analysis is one of the more effective and widely accepted methods of conducting forensic schedule analysis. Creation of a mid-period, or progress-only, schedule is essential to effective Windows analysis, in that it separates the effects of progress on the critical path from the effects of revisions to the network, thereby isolating causes of delay from efforts meant to mitigate those delays. AACE’s Recommended Practice for Forensic Schedule Analysis outlines methods for creating mid-period schedules; however, Primavera Version 6 has introduced a wide variety of new functions which, while beneficial to project managers during construction, may cause problems with the creation of mid-period schedules during delay analysis. As a result, there is a risk that the advanced global features of enterprise scheduling software, like P6, can introduce errors into the created schedules. In addition to making recommendations for best practices in creating mid-period schedules, this paper will examine the risks and potential sources of error, through case studies, and make recommendations for tracking, mitigating, or eliminating risks associated with the creation of mid-period schedules.
CDR-0974 | When an Owner's Hard-Line Claims Negotiations are Also a Breach of Contract | Christopher J. Brasco; Adam M. Tuckman | 2012 | This paper will explore the boundaries separating an owner’s negotiation posture from a breach of the duty of good faith and fair dealing. The reader will gain a fuller understanding of the owner’s responsibilities in the changes process so that they can more effectively administer the contract change order process. In particular, this paper will focus on the evolving legal requirements defining the owner’s duty of good faith and fair dealing when handling contract changes. It will also inform the reader of the implication of a public owner’s actions in its varying capacities ranging from public representative to contracting party. Thereafter, the authors’ will present possible consequences of an owner’s breach of his or her duty of good faith and fair dealing. The presentation of this topic will relate practical experiences with the administration of contract changes, how the process can be best administered in the interest of all concerned, and the negative consequences of a breach of the duty of good faith and fair dealing.
CDR-0978 | Evaluating Cost Escalation Using Cost-loaded Schedules | Sagar B. Khadka, CCE PSP; Christopher J. Payne, PE CFCC PSP | 2012 | Predicting costs of labor, equipment and materials is an intrinsic challenge in construction contracting. The cost of materials for long-term capital construction projects can be unpredictable and swing in either direction during the project performance period. For instance, the construction industry encountered a steep up and down variation in the price of steel during the last decade, creating a highly volatile market environment. When a time extension is awarded to a contractor because of an owner-caused delay, the inclination on the contractor’s part might be to expect a materials cost escalation payment for the difference between the bid price and the materials price at the time of purchase. However, that simplistic approach may not reflect all aspects of the cost increase, including the contractor’s risk of escalation absent owner delay, the anticipated time of material purchases, and actual material procurement during the project. This presentation will share how such cost escalation claims were evaluated for a large capital construction project, spanning seven years, using the combination of cost-loaded schedules and the relevant materials price analysis.
CDR-0980 | Proving Engineering Productivity Loss | Tong Zhao, PE PSP; J. Mark Dungan | 2012 | The measured mile/baseline method has been widely accepted to quantify labor productivity loss, but it has not been successfully used in engineering productivity because of the challenges in engineering productivity measurement and the determination of productivity benchmark. This paper presents a series of procedures based on the measured mile/baseline method to quantify engineering productivity loss from a project specific perspective. A case study on the piping discipline in a large scale process plant project is used to illustrate the calculation. The paper also includes a proposed approach, the two mile method, to quantify engineering productivity loss using data for similar work, but different complexity.
CDR-1003 | Proving the Hidden Costs of Acceleration | Robert A. Dieterle, CCE; Thomas A. Gaines, CCC | 2012 | The most critical milestone of any project, with few exceptions, is the final completion date. Failing to achieve this target can mean lost revenues for the owner and liquidated damages for the contractor, among other undesirable effects. In the face of project delays, a contractor may make the decision to accelerate. At times, the contractor will be compelled by the owner to accelerate its performance in order to meet certain milestones in accordance with the original schedule or a revised plan for completing the project. This paper will discuss the costs of different types of acceleration programs, along with the inherent risks and benefits associated with each approach. What does a contractor need to understand and communicate in order to know or prove its full impact? The discussion will focus on the often unforeseen costs of acceleration and will attempt to prompt decision-makers to ask the question: Is the benefit of accelerating the work going to outweigh the ultimate cost?
CDR-1212 | Forensic Analysis of Superstorm Sandy Damage | William M. Hart, PE CFCC PSP | 2013 | When Superstorm Sandy approached the New Jersey Shore in late October 2012, there was an expectation by weather professionals and government agencies of a storm of historic proportions. However, all the warnings in the world could not have prepared New Jersey, New York, and other areas impacted by the storm for the devastation and tragedy that Sandy brought. Extensive news coverage of Sandy has described the devastation in detail: more than 650,000 housing units damaged or destroyed, primarily as a result of the storm surge, along with numerous business locations, many of which will never recover. With Sandy striking as “just” a superstorm and not a hurricane, determining the damage mechanism, particularly wind versus storm surge, is a critical issue in the insurance claims process for all property owners. Many policies cover damage caused by wind but not damage caused by storm surge, which is often considered flood, and therefore excluded or subject to extremely high deductibles and aggregated sublimits. Therefore, there has been considerable conflict between property owners and insurers as to the determination of the specific cause of Superstorm Sandy damage. Typically, when this conflict arises, a forensic construction expert or investigator is brought in to help resolve the issue. However, beyond the analyses of all the available data, there are many other challenges facing the forensic construction expert or investigator. In this case, such challenges include seeing “beyond the headlines” of Superstorm Sandy, while gathering all available information to formulate substantiated conclusions regarding the cause and origin of property damage.
CDR-1213 | An Introduction to Dispute Boards and All Its Forms | James C. Perry | 2013 | This paper reviews the workings of an alternative dispute resolution mechanism broadly known as a Dispute Board. Dispute Boards are a form of adjudication, or conciliation, featuring a panel of experts named at the outset of the project. The Board visits the job site regularly during construction and keeps current on the project’s progress, even when there are no formal disputes. This paper covers the historical beginnings of Boards in the Americas, through their adoption by FIDIC (International Federation of Consulting Engineers) in their standard forms of Contract in 1999, and later by many multilateral development banks and international finance institutions, notably through the promulgation of the FIDIC MDB version of its Construction Contract issued first in 2005, and also through the publication and promulgation of the ICC Dispute Board Rules in 2004. The paper also describes the various types of Boards found in the FIDIC suite of contracts (standing and ad hoc) and rules for the use of the various Boards under the ICC Rules (DRB, DAB and CDB). The mechanics of operation are covered, and the advantages of the systems, especially the forms which allow the Board to play an advisory role.
CDR-1240 | Trends in International Construction Arbitration | Peter V. Badala; James G. Zack, Jr. CFCC | 2013 | International arbitration is a transnational dispute typically involving disputes between parties from different nations often performing work in yet another nation. A UK contractor constructing a ore processing facility in a sub-Saharan African nation on behalf of a Canadian minerals company, files a claim for UK£1.45 million and seeks arbitration when the project owner refuses to settle is a an example of an international arbitration. As the world’s economy has become more globalized, more corporations are working internationally. Over the past two to three decades disputes on construction projects have become larger, more complicated and more common. A literature survey indicates that arbitration is the preferred dispute resolution mechanism for international corporations rather than transnational litigation. As the number of arbitration case filings has increased so has the number of arbitral institutions (which now number at least 28) and the seats of arbitration. Perhaps in reaction to growing criticism of the process, there has been and continues to be other changes concerning international arbitration.
CDR-1246 | Avoiding the Pitfalls in Implementing the Measured Mile Method | Tong Zhao, PE PSP; J. Mark Dungan | 2013 | The measured mile method, a widely accepted approach involved in lost productivity claims, compares the productivities of identical or similar work between non-impacted or least impacted and impacted segments of a project. The procedures to implement a measured mile study usually include data processing, productivity measurement, measured mile identification, cause and effect analysis, and loss of productivity calculation. Despite the popularity of the measured mile method, incorrect implementation can cause failures in proving and quantifying loss of efficiencies for claims that resulted from the impacts legitimately assignable to other parties. This article discusses some common errors and pitfalls in implementing the measured mile method in loss of efficiency claims, which should be avoided. A case study, demonstrating how to turn a loss of efficiency claim from implausible and counterintuitive to well supported with causation by correcting a few subtle errors in implementing the measured mile method, is also presented.
CDR-1254 | EOT Claims: Successful Navigation through a Legal and Technical Minefield | Anamaria I. Popescu, PE PSP; John C. Jerz | 2013 | Extensions of time claims (EOTs) continue to be a practical and legal minefield for a principal and contractor alike. For a contractor, an extension of time claim can be the most expedient and successful method of recovering delay costs. However, the question of entitlement to an EOT should always be examined from both a legal perspective (by reference to the contract) and also a practical perspective (by reference to the contemporaneous schedules and project records). This paper focuses on the methodology a contractor should employ to prepare a compelling EOT claim. First, the triggers giving rise to an EOT claim will be explored along with contractual entitlement. Next, the key ingredients necessary to create an effective EOT claim are described. Finally, discussion involving the correct documentation and presentation of an EOT claim is explained along with the timing of the submission.
CDR-1256 | Challenges of the Measured Mile Concept for Productivity Loss Claims | Philip D. Barnard, PE CCE | 2013 | Contractors face several challenges when developing claims for productivity loss due to owner/architect/engineer or third-party interference. These include the burden of linking the interference to the productivity loss and establishing the reasonableness of estimated increased time and/or costs. AACE International describes various methodologies in its Recommended Practice No. 25R-03 for estimating lost productivity, with the most favorable being the Measured Mile. This paper discusses this methodology in which labor performance is compared between two time periods – an unimpacted period called the “Measured Mile” and an impacted period. This paper discusses the challenges in comparing Measured Mile performance criteria, including work tasks, productivity levels, worker skill levels, work scopes, and work environment. By following the guidelines outlined in this paper, contractors and claim preparers can ensure they are utilizing the best available facts and records to package their claim in an understandable and believable format to ultimately be successful in their recovery of damages.
CDR-1273 | Forensic Schedule Analysis on Risk Adjusted Schedules | John C. Livengood, CFCC PSP; Patrick M. Kelly, PE PSP | 2013 | With increasing time and cost pressure from owners, it is likely that risk-adjusted schedules will expand beyond their current uses and become more common in buildings and infrastructure construction. Risk-adjusted CPM schedules use computer modeling to analyze the likely fluctuation of activity durations resulting from a range of uncertainties and risks, and then analyze the effects of the variations on the schedules float as different chains of activities are given different durations and the amount of float changes. The result is a schedule that has a series of potential critical paths with varying degrees of likelihood, rather than a single Critical Path and sub-critical paths. Forensic schedule analysis, however, is predicated on identifying the “single” contemporaneous critical path, often defined as the path with zero float. So what happens when the CPM schedule series has been risk-adjusted so that float is variable and more activities paths are critical? This paper will discuss a theoretical model for performing a delay analysis on a project where the initial baseline and all updates were adjusted for risk.
CDR-1278 | Disruption Analysis by CPM Out-of-Sequence Methodology | Fredric L. Plotnick, PE | 2013 | Delay to an activity may not lead to delay of the project. However, such delay may lead to a disruption to the contractor’s anticipated means and methods and be the basis for a claim. Delays imposed upon many activities may also lead to a resource driven delay to the project. This presentation will address a means to determine the costs of disruption at the activity level and to analyze the cumulative impact to cost and schedule at the project level. This analysis may then be compared to the more traditional methods of measurement of impact of disruption, such as the measured mile approach to determine loss of productivity, and other “big picture” analyses.
CDR-1356 | Windows Analysis versus Half-Step Analysis Progress Impact Quantification | Greta A. Martin, PE PSP | 2013 | Although categorized separately, AACE’s Recommended Practice 29R-03 “Forensic Schedule Analysis,” indicates that Windows Analysis (MIP 3.3) and Half-Step Analysis (MIP 3.4) are nearly identical. As part of the same family of analyses, both methods use contemporaneously generated schedules, evaluate impact to the schedule from one update defined time period to the next, and take into consideration changes to the critical path via both progress and schedule revision. However, the key divergence between the two approaches is the creation of mid-period schedules in the Half-Step Analysis. As a result of this added step, and despite the methods’ similarities, these analyses can yield different results regarding delay quantification of in-period progress versus schedule revisions. Using a series of case studies, this paper explores the similarities and differences in the application of these methodologies, and will explain and quantify potential disparities in the end results.
CDR-1382 | Schedule Activity Density Analysis | Jeffery L. Ottesen, PE CFCC PSP; Kenji P. Hoshino, CFCC PSP | 2013 | Given inherent difficulties in construction, optimizing labor efficiencies is paramount, while failure bleeds profit margin and can cause critical delay. Correlation between productivity loss and delay is not always apparent, thus making proof of cause and effect for productivity loss an arduous task. Such proofs typically rely upon contemporaneous records related to schedule and resources. Resource loading and leveling a CPM schedule has been around for decades, but not enough schedules fully utilize such capabilities. Common to all schedules, however, are planned work activities and logic (whether specific or implied) that define intended work sequence. Whether resource loaded or not, these activities represent to some degree a coordinated management effort of time and resources. This paper presents a means to quantify and analyze schedule activity densities pursuant to identifying productivity loss in real-time, or in retrospect when supporting a claim.
CDR-1402 | Mis-Using the Measured Mile Concept to Make a Claim | Robert D. Kelly, Jr. CFCC PSP | 2013 | In construction, the “Measured Mile” is a frequently-cited damage calculation methodology associated with claims for loss of labor productivity. There is no single implementation for the Measured Mile - it is more concept than prescription. Proper Measured Mile claims are compelling. However, recent trends in Measured Mile claims represent a transformation and weakening of the otherwise reliable and repetitiously-lauded methodology. The purpose of this paper is to identify, through actual and recent examples, trends in claims which represent a diminishing transformation of the Measured Mile methodology. Given the expanding spectrum of Measured Mile claims, there is a need for the industry to structure nomenclature, protocols, and a hierarchy of implementation such that Measured Mile claims can be properly associated with new and varying accolades (or criticisms) of the different ways to perform the calculation.
CDR-1404 | Adapting Alternative Dispute Resolution to Meet the Demands of Modern Projects | Christopher M. Anzidei; Christopher J. Brasco; Adam M. Tuckman; Blake V. Peck, PE; Brian M. Perlberg | 2013 | Complexity and uncertainty have become hallmarks of modern construction projects. Over the past two decades, our industry has experienced rapid changes that have fundamentally transformed the industry. Advances in technology and innovation have changed the way projects are planned, constructed, and monitored. Speed to the market has become a premium. Shrinking budgets and alternative delivery methods have presented unique challenges and caused a realignment of project partners, with a marked shift away from the traditional design-bid-build model. And we are still suffering from a global recession, the worst in 80 years. The rapid rate of change and new alignments of project participants have placed a premium on efficient, timely dispute resolution. Our paper will examine commonly-used ADR (Alternative Dispute Resolution) methods (e.g., mediation, arbitration, DRBs, project neutrals) and discuss how these mechanisms can be adapted to meet the needs of modern projects. Gone are the days when parties can simply reserve rights and fight later. Rather, the authors will suggest ways in which participants can incorporate efficient, effective dispute resolution techniques into their projects.
CDR-1436 | Generating Claims through Contract Provisions and Management Practices | Mark F. Nagata, PSP; Frank DiCianni | 2013 | Nobody is pro claims. We are all claims avoiders. We all partner, whether in name or just deed. Yet claims continue to be filed and we continue to be mired in litigation or tamer, but still costly, mediation and arbitration. The purpose of this paper is to explore why our stated objective of claims avoidance does not always fit with reality. Perhaps some claims are inevitable, but the focus of this paper will be on contract language and construction management practices that function as “claims generation machines.” Their operation is not obvious, but too often effective. Specifically, these machines are: 1. Managers who do not “believe their indicators” and don’t act to resolve delay-related issues timely. 2. Management practices that push off the resolution of time extension request to the end of the project. 3. The willingness or need for individuals at different levels in an organization who are willing to pay for items that the contract itself forbids. 4. Contract provisions that resolve disagreement over the pricing of additional work differently. 5. Contract provisions that fail to consider all of the potential costs of a change.
CDR-1510 | Trends in Construction Claims & Disputes | James G. Zack Jr., CFCC | 2014 | Claims and disputes are a constant in the construction industry, regardless of whether the industry is doing well or poorly. The number of claims seems to have risen during the recent recession despite the downturn (or perhaps as a result of the downturn) in the industry. This paper, based on research conducted by the Navigant Construction Forum™, overviews some relatively recent trends related to construction claims and disputes in the areas of concurrent delay, suspensions of work, time extensions, notice and claim filing requirements, calculation of home office overhead, proof of differing site conditions and risk transfer in the design/build environment under Federal government contracts. Through this insight, it is believed that owners, design professionals, construction managers, contractors and subcontractors can devise ways to avoid such issues going forward thus making projects more successful, and more profitable, for all stakeholders.
CDR-1526 | Ranking AACE International’s Forensic Schedule Analysis Methodologies | Robert M. D’Onofrio, PE | 2014 | AACE International’s Recommended Practice 29R-03 Forensic Schedule Analysis (“RP29R-03” or “the RP”) identifies various methods for conducting schedule delay analysis, but does not recommend or apply any preference amongst the methods. This article uses RP29R-03’s guidance to rank the methods in RP29R-03, and compare that ranking result with a ranking of methods in the Society of Construction Law’s Delay and Disruption Protocol and with a ranking of methods based on US legal decisions. All three analyses reach similar conclusions with respect to preferred method ranking and order. Despite the fact that the name of a method is not as important as how it is implemented, ranking the RP29R-03 methods based on the guidance in RP29R-03 is useful for high level discussion to reduce debate over methodology and to reduce usage of lower ranked methods that are technically flawed.
CDR-1554 | A Method of Improving Delay Costs Calculations | Barry Allan Tozer | 2014 | The paper provides an alternative method of calculation of field overhead delay costs where productive work is being undertaken concurrently with a critical path delay. The limiting case where no concurrent work is undertaken is non-controversial. In that case, the total delay cost is calculated from the delay period ascertained from the critical path and the average daily actual time-related field overhead cost. Where work is continuing on unaffected parts of the site or unconnected activities, this approach invariably overstates the actual delay cost. The alternative methodology calculates an expected time-related field overhead cost as a percentage of the direct cost of the work being undertaken concurrently for each time period. That amount is deducted from the actual time-related field overhead for that period to determine the delay cost component. This cost per time period is accumulated over the delay period to determine the likely actual delay cost. The alternative methodology may be presented graphically so that the impact of the delay on field overhead costs in each time period is better understood.
CDR-1593 | Forensic Schedule Analysis Methods: Reconciliation of Different Results | John C. Livengood, CFCC PSP; Patrick M. Kelly, PE PSP | 2014 | Perceived wisdom within the construction industry is that different Forensic Schedule Analysis (FSA) methods produce different results on the same set of facts. Although there are many potential variables that could cause this, such as bias of the analyst or the quality of the implementation of a method, some experts have expressed concern that the methods themselves generate different results and are therefore some may be potentially defective. But do the different methods actually generate different answers when applied properly to the same set of facts, or are the observed differences natural aspects of the methods that can be documented and quantified? This paper will explore that question by examining a specific set of facts and applying each of the four major FSA methods – the As-Planned vs. As-Built, Contemporaneous Period Analysis, Retrospective TIA, and Collapsed As-Built – to those facts. Further, if the methods do generate different results, the paper will explain how and why that occurs, how to quantify and reconcile the differences, and what conclusions a FSA expert should draw from those differences.
CDR-1632 | Great Debate: Is Cumulative Impact a Provable Reality? | Patrick C. Kelly, PSP; Robert Kelly Jr., CFCC PSP; Mark Nagata, PSP; Dr. Anamaria Popescu, PE PSP | 2014 | The concept of Cumulative Impact is one of the most controversial areas of construction claims. Conceived during a time when measurement of productivity was difficult, Cumulative Impact claims seek to account for additional labor costs which are not directly attributable to an individual change order, but are instead allegedly the result of the aggregated and “synergistic” effects to productivity of an excessive number of changes to a single contract. Despite case law supporting its existence, forensic schedule analysts continue to raise questions about this controversial claim. Does Cumulative Impact exist, or was the rationale flawed from inception? Is it possible to segregate productivity losses in order to define specific cumulative impact losses, or is a Cumulative Impact claim always a “total productivity loss” claim? And is there a way for a contractor to put together a claim that an owner will ever find acceptable? This paper will provide an overview of the theory behind these claims, and will address the arguments for and against Cumulative Impact claims, highlighting the key areas of the controversy.
CDR-1659 | Lost Productivity – Finding the Missing Puzzle Pieces and Contract Bars | Dr. Tong Zhao, PE PSP; J. Mark Dungan | 2014 | A contractor makes certain assumptions regarding the scope of work represented in a contract, specifications and drawings, construction sequence, and schedule. Should those conditions change, the contractor may suffer economic losses related to unplanned extra effort. However, in the case of lost productivity, identifying the cause and effect is often illusive and in some cases contracts even try to explicitly bar loss of productivity claims. This paper discusses loss of productivity, an important piece in the construction claim puzzle, and employing the measured-mile methodology to prove the damage. This paper also discusses potential methods of recovering extra labor when loss of productivity claims are explicitly denied in the contract.
CDR-1669 | Performing Forensic Analysis on Complex EPC Schedules | Michael Dennis, CCP | 2014 | This paper is a review of the problems faced in forensic analysis with increasingly larger and more complex project schedules for EPC contracts. It will cover the potential problems caused during the life-cycle and evolution of the project schedule. Along with the problems that are encountered during and at the end of the job, due to the schedule size, complexity and the issues caused by the scheduling software. It will discuss analysis techniques for analyzing these massive schedules forensically (summarization, EPC individually, period by period, etc...) along with potential pit falls to avoid.
CDR-1683 | Untangling Concurrent Delay on Pipeline Projects | Greta Martin, PE PSP; Jeffery L. Ottesen, PE PSP CFCC | 2014 | Construction projects for pipelines, utilities and highways typically follow linear-sequenced work plans. Such projects literally begin at a point “A” and end at a point “B”. In CPM terms, there may be only a single critical path, or a single string of planned activities that define the entire scope of work. Such schedules seem simple in principle and design, and because of this simplicity, contractors and owners frequently spend less time developing the schedule and simply ‘dive into’ the construction work. If preparing such a schedule is so simple, why then do so many linear projects experience delay and pose contractors difficulty in proving cause and effect? This paper considers concepts of delay concurrency, distinguishes between literal concurrency and functional concurrency, and presents issues schedulers, experts and triers of fact should consider when confronting concurrency on linear projects.
CDR-1696 | Implementing Complex Time Impact Analyses on Oil & Gas Projects | Ronald J. Rider; Rod C. Carter, CCP PSP | 2014 | AACE International’s Recommended Practices for Forensic Schedule Analysis (29R-03) and Time Impact Analysis - As Applied in Construction (52R-06) provide general guidelines for inserting delay events to impact a schedule. In practice, creating and adding delay events and modeling their schedule impacts can be quite complex, especially on highly impacted oil & gas projects that span several years. This paper discusses the inherent complexities and provides practical considerations and methods for:  Creating fragnet activities and statusing them across multiple analysis windows  Quantifying extended durations to account for additional work  Tying fragnets to impacted activities using Finish-to-Finish (FF) logic  Evaluating Contractor-responsible delays that are embedded in Owner-responsible events The methods discussed in this paper are drawn from the authors’ experience in implementing retrospective Time Impact Analyses (MIP 3.7 Modeled/Additive/Multiple Base) on large EPC oil and gas project disputes. The examples are drawn from a 6,000-activity schedule on a gas plant project impacted by hundreds of changes and delayed by 16 months.
CDR-1713 | Macro-economic Impact of Payment-related Construction Delays in Nine Emerging Markets | Dr. Jay Palmos, CFCC PSP | 2014 | The role and importance of the construction sector varies from one country to another. In countries with established infrastructure and urban areas the sector plays a far less significant role in the national economy than in developing countries. This study investigates the macro-economic impact of payment-related construction delays in nine emerging markets. It is suggested that those countries which have systematic and pervasive construction delays due to payment-related issues will necessarily suffer in proportion to the percentage of GDP made up by the construction industry economic cycle. It is recommended that those countries where construction sector comprises a significant proportion of GDP and who report payment related issues as the most frequent cause of construction delay should adopt a Security of Payment style legislation.
CDR-1730 | Why Collaboration is the Key to Successful Projects | Christopher M. Anzidei; Christopher J. Brasco; Adam M. Tuckman; Robert Fraga; Ralph Kreider | 2014 | Collaboration is an oft-used buzz word in the modern construction industry. Given the thin line separating winning and losing projects, collaboration can no longer be left to chance. For this ideal to be realized, it must be the subject of thoughtful planning. The parties can foster meaningful collaboration by devoting their attention to several important factors in planning and executing their project. These factors include selecting the appropriate delivery system and project team, properly allocating risk in the contract documents, implementing a system to identify and manage risk during performance (including both cost and schedule controls), establishing incentives for positive performance, and utilizing efficient dispute resolution methods. Our paper will explore these means of aligning the parties’ efforts and offer practical tips for how the parties can foster true collaboration in planning and executing their contracts. Furthermore, while unforeseen circumstances occur on every project that give rise to changes, these need not put the project team at odds. Accordingly, we will also address means by which the parties can break impasses without breaking relationships.
CDR-1757 | Pricing and Proving Delay Claims | Michael Berta; Joshua Ritti | 2014 | While many construction projects experience delays, properly pricing and proving the delays has become increasingly difficult as owners have learned to limit their exposure to delay claims. This paper will provide a methodology to price and prove delay damages on any type of construction project. The paper will identify common pitfalls and mistakes made when developing delay claims. It provides an overview and comparison of schedule delay analysis methodologies commonly employed by scheduling experts, providing both advantages and disadvantages of each method. It will explain how a contractor’s accounting system can be used to price and prove a delay claim. The paper discusses contract clauses used by owners to limit delay damages and ways contractors can counter such contractual obligations. This paper will leave the reader with an understanding of how certain scheduling and delay damage calculations that are widely accepted in the construction industry can be employed to help quantify the damages resulting from unforeseen time impacts and maximize the opportunity for recovery of damages resulting from such impacts.
CDR-1815 | Forensic Schedule Analysis and Discretionary Logic | John C. Livengood Esq., CCP CFCC PSP | 2015 | Forensic Schedule Analysis (FSA) and real time schedule reviews do not handle CPM schedules with significant amounts of discretionary logic very well. In the last decade, major theoretical and practical advancements have been made of which FSA methodology is most appropriate to evaluate schedule delay, largely through the introduction of AACE’s RP29R-03. Nevertheless, discretionary logic - the type of logic that is not dictated by either the contract or the construction necessity of the project - continues to cause difficulty in creating fair and accurate analyses of schedules during the course of the project. Further, these analytical problems persist in the methodologies associated with post-construction FSA. This paper considers several applications and refinements of existing forensic delay methodologies, particularly As-Planned vs. As-Built, which can assist in identifying the as-built critical path and delay responsibility in projects with significant amounts of discretionary logic.
CDR-1868 | Changing Trend in Risk Allocation - Differing Site Conditions | Steven A. Collins; James G. Zack, Jr., CFCC | 2015 | This paper perspective has been prepared by the Navigant Construction Forum[TM] authors in order to explore a series of Court and Board of Contract Appeals decisions concerning coverage of the Differing Site Conditions clause. While preparing an earlier paper entitled "Trends in Construction Claims and Disputes" the authors noted that there have been a series of decisions issued by Courts and Boards of Contract Appeals over time which seem to be increasing contractor risk under the Differing Site Conditions clause. This paper explores such decisions and highlights the risks for contractors concerning differing site condition claims. The paper also draws conclusions and sets forth some practical recommendations for both owners and contractors in dealing with the risks of differing site conditions.
CDR-1878 | US Major Task Order Contracting and NZ Collaborative Alliances Comparison | Jorge Rueda-Benavides; Dr. Eric Scheepbouwer; Dr. Douglas D. Gransberg, PE CCP | 2015 | Project delivery models that use a relational contracting approach, and operate using an increasing level of integration for the delivery, are becoming more prevalent and are touted to be the "magic bullet" to eliminate disputes and maximize collaboration. Such contracting mechanisms, known in New Zealand as alliancing contracting, have been in use in this country for over two decades and are becoming ubiquitous in Australasia for the delivery of complex infrastructure construction projects. Alliancing's key characteristic is a "no litigation" clause that has led US agencies to shy away from it as impossible to implement under US law. This paper argues that the US Department of Defense's major task order contract is very similar to the collaborative alliance contract currently in use to deliver the massive reconstruction program estimated at approximately NZ$2.5 billion in Canterbury, New Zealand. The paper compares case studies of a US and a New Zealand project and finds that US public owners can accrue most of the advantages provided through alliancing contracting without the need to include a "no litigation" clause.
CDR-1920 | Minimizing Financial Losses Using Builder's Risk Insurance | Dayna L. Anderson; Seth D. Lamden, Esq. | 2015 | Damage to work, materials, and equipment during construction can impair the ability of project stakeholders to meet budgetary and scheduling targets. Delays resulting from the repair and replacement of damaged work can lead to other unanticipated expenses, including lost revenue, additional carrying costs, and other so-called "soft costs." Builder's risk insurance is often the most effective way to manage these unanticipated costs and delays. However, the coverage provided by the builder's risk policy should be consistent with the expectations of all parties that have an insurable interest in property related to the construction project. This article provides an overview of the types of coverage provided by a builder's risk insurance policy and discusses policy provisions that can lead to coverage disputes between builder’s risk insurers and their insureds. This article also provides recommended practices for an insured to follow when presenting a claim to a builder's risk insurer to avoid or minimize the impact of coverage disputes.
CDR-1967 | Determining the Measured Mile for Lost Productivity Claims | Dr. Tong Zhao, PE PSP; J. Mark Dungan | 2015 | Proving and quantifying lost productivity is one of the most challenging areas in construction claims. Among the available approaches, the measured mile method is ranked as the most preferred method to quantify lost productivity according to AACE International. The method is preferred, in part, because it eliminates disputes over the validity of the original estimate by comparing actual productivity of similar work, with the primary difference being the impacts in question. Since the distinction between the impacted and non-impacted sections in many projects is not readily observable, researchers and professionals have developed various procedures to help identify the measured mile. In the paper, the authors will review various techniques that have been developed previously and present their Improved Baseline Method.
CDR-1997 | An Improved Measured Mile Methodology for Heavily Disrupted Projects | Nelson L. Gallardo | 2015 | Construction projects are often impacted by specific disruptive events that occur during defined periods of time affecting the planned productivity of work activities within a construction sequence. Typically, in construction disputes, the Measured Mile methodology to calculate lost labor productivity is used as it is considered the most precise calculation method and therefore, the most recognized approach when claims are presented in arbitration proceedings. However, the normal application of the Measured Mile is not recommended to analyze lost productivity in activities that are continuously disrupted. This limitation can be overcome by the use of a baseline Productivity Analysis that generates a more precise calculation where no specific Measured Mile periods are available. This paper is a case study of the application of a baseline method in a heavily and permanently impacted project to demonstrate that the traditional Measured Mile is not a “Cure All Medicine”.
CDR-2013S1 | (Presentation Only) Concurrent Delay - The Owner's Newest Defense | James G. Zack, Jr. CFCC | 2013 | When owners impose liquidated damages at the end of a delayed project contractors often respond with allegations of concurrent delay. That is, contractors argue that some or all of the project delay was actually caused either by the owner or an external force, concurrent with the contractor’s delays, and therefore liquidated damages should be forgiven or excused. As owners generally do not impose liquidated damages until the end of the project, frequently a contractor’s claim of concurrent delay is not submitted until the project is complete. This presentation explores mechanisms, based on recent court rulings that owners employ to defeat a contractor’s “concurrent delay defense”.
CDR-2013S2 | (Presentation Only) Time Extension Requests - A Checklist | James G. Zack Jr. | 2013 | Whether an Agency CM or a CM@Risk, construction managers must learn to analyze and justify their decisions concerning time extension requests. As an Agency CM it is not uncommon for the construction manager to be tasked with the responsibility of receiving, analyzing and recommending a course of action on time extension requests submitted by contractors. As a CM@Risk the construction manager may be called upon to submit a time extension request on their own behalf and/or analyze time extension requests submitted by their subcontractors. This presentation identifies the tests that have been set forth by the Federal Courts to justify an excusable or compensable time extension. The presentation discusses how these rules are applied, whether submitting or analyzing, a time extension request. The presentation discusses the rules concerning concurrent delay and how the courts hold the claimant responsible for allocating concurrent delay. Finally, the presentation highlights two new court rulings which may be “game changers” concerning delays, time extension requests and defense against liquidated damages.
CDR-2047 | Unified Evaluation Criteria for Delay and Productivity Analyses | Kenji P. Hoshino, CFCC PSP | 2015 | This paper dispels the perceived inconsistency on methodology ranking between AACE Recommended Practices 25R-03 for Loss of Productivity on one hand and 29R-03 for Forensic Schedule Analysis on the other. By distinguishing “ranking of methods” from “evaluation of implementation”, it paves the way for a meaningful dialog among practitioners and users for a unified set of criteria for a systematized and reliable evaluation of both CPM delay analyses and loss of productivity analyses.
CDR-2114 | Structuring Construction Claim Investigation Processes to Reduce Cognitive Bias | Dr. Amin Terouhid, DRMP PSP; Dr. Maryam Mirhadi Fard, PSP | 2016 | Research in cognitive science has studied a variety of psychological constraints on human information gathering and processing. Some forms of deviation in judgment due to these constraints are referred to as cognitive bias. Seeing matters in an unjustifiably positive light, a preference for the use of more recent information, being overly influenced by initial information, and giving credit to causation where evidence solely suggest a correlation are four examples of these biases. Claim investigations are subject to potential adverse effects of cognitive biases in a variety of ways. This study investigates how claim investigation processes should be structured to systematically reduce the effect of cognitive bias on the outcomes. A questionnaire survey, conducted amongst construction claim attorneys and claim professionals, helped to better identify cognitive biases that adversely affect construction claim investigation and prepare a reliable list of strategies for minimizing cognitive bias in claim investigations.
CDR-2181 | Proving Loss of Efficiency and Extra Work Claims | Robert M. Freas; Muhammad Khedr, PSP | 2016 | For proof of any construction claim, one must demonstrate liability, causation and the resulting damages. In order to prove causation and the resulting damages, the claimant needs to rely upon the project documentation and its job cost accounting system, which may not be prepared nor managed properly with claims in mind. Circumstances may arise which leave the contractor no choice but to prepare a claim to demonstrate causation, and then quantify the resulting damages caused by loss of efficiency and extra work. This paper will identify common mistakes made when preparing project documentation that is essential to developing entitlement for loss of efficiency and extra work claims. It also provides an overview of loss of efficiency analysis methodologies commonly employed by experts. The paper will examine how a contractors accounting system can be used to price and prove loss of efficiency and extra work claims.
CDR-2183 | The CALDARERA FORMULA™ Calculating the Daily Rate of the Contractor | Joseph V. Caldarera, PSP | 2016 | It is not uncommon to face Owner opposition on a delayed or disrupted construction project when attempts to quantify a delay are presented. Even when schedule analyses that prove the number of entitled compensable delay days are offered, the argument regarding remuneration for economic loss becomes a point of contention. Existing formulas that purport to determine a Daily Rate consider the total work program of the Contractor. Such methods of establishing a Daily Rate are not project specific, and are imposing to the Contractor. The CALDARERA FORMULA™ is project specific, and simplifies the evaluation of the Daily Rate by using contractual mechanisms, such as the Baseline Schedule and Schedule of Values, which identify the original Contract Time and Contract Sum, respectively. Contractually, the Schedule of Values is to be used to establish all payments under the contract. Thus, a simple arithmetic calculation to quantify the Daily Rate of the Contractor is enabled. The CALDARERA FORMULA™ is simple, compliant with the Contract Documents, and easily explained.
CDR-2192 | Different Allocation Methods for Indirect Costs | William C. Schwartzkopf; Cory R. Milburn, PSP | 2016 | A common methodology used to allocate indirect costs on a project, which has been extended, is to allocate based on time, usually in the form of cost per day. A time based allocation may not be the most appropriate methodology because the driving factor for some costs, particularly costs such as equipment, small tools, supervision, and expendable items, is direct labor cost or direct labor hours. A more appropriate method to allocate those indirect costs is as either a percentage using a labor cost as the driver or as a cost per direct labor hour with labor hours being the driver. This paper compares the results of using a cost allocation base of direct labor hours to other allocation methods such as actual cost compared to adjusted, cost per day, and period based costs.
CDR-2211 | Finding the Elusive Measured Mile: Unconventional Case Studies | Dr. Tong Zhao, PE PSP; Mark Dungan | 2016 | The measured mile method (including the baseline method) is generally the most preferred approach to prove and quantify lost productivity in construction projects, yet applying the method can be challenging. The measured mile method uses project specific data to compare the actual productivities on identical or similar work between unimpacted or least impacted and impacted periods or segments of a project. The application of the measured mile method is often abandoned due to the lack of suitable productivity data, difficulties in proving similar work, and sometimes unclear distinction between the unimpacted or least impacted and impacted periods or segments. This paper demonstrates, through case studies, the techniques used by the authors to apply the measured mile method when it may intuitively appear inapplicable. It is hoped that practitioners will be inspired by the ideas discussed in this paper and learn innovative applications for the measured mile method.
CDR-2212 | Choosing the Most Appropriate Schedule Analysis Method | Andrew Avalon, PE PSP | 2016 | AACE International’s Recommended Practice No. 29R-03 for Forensic Schedule Analysis (RP 29R-03) presents nine different methodologies for performing schedule analyses. Some schedule analysis methods are better suited for certain purposes than others. Each method is unique in its applicability to a given set of project specifics, including: type of project, legal jurisdiction, contract documents, dispute resolution mechanism, fact pattern, and other project execution factors. A mismatch between project specifics and the selected methodology can substantially undermine a party’s chance of recovery, add unnecessary costs, and distract from factual entitlement issues. Familiarity with the key elements of RP 29R-03 and a clear understanding of the core assumptions, strengths and weaknesses of the recommended methodologies is a basic, yet critical, step for properly implementing a schedule analysis. This paper presents an overview of each of the nine schedule analysis methodologies, the nomenclature used to categorize the different methods, and the strengths and limitations of each method. It then discusses eleven factors a forensic schedule analyst should consider when choosing the most appropriate schedule analysis method.
CDR-2235 | Retrospective TIAs - Is There a Better Way? | John C. Livengood, CCP CFCC PSP FAACE | 2016 | The power of Time Impact Analysis (TIA) methodology is attested to by its near universal adoption as a preferred method to establish entitlement for time extensions during the course of a project using CPM scheduling. The AACE RP 52R-06 (2006), which provides a detailed explanation of how to properly perform this prospective analysis, is further example of Prospective TIA’s importance. Yet, at the same time, Retrospective TIAs continue to pose significant methodological issues even though it remains a major methodology for determining the delays in a CPM schedule, as reflected in the AACE RP29R-03 (2011). Questions concerning retrospective TIA’s accuracy abound as originally reflected in the question posed in the 2008 AACE presentation on the matter: “Retrospective TIAs – Time to Lay Them to Rest?” After nearly four decades of use, this article presents a case as to why the use of forensic TIAs should be sharply restricted due to its defects and the alternatives that are available to the expert analyst.
CDR-2236 | Mixed Forensic Schedule Analysis Methodologies – Proceed With Caution | Roger Nelson, PE; John C. Livengood, CCP CFCC PSP FAACE | 2016 | Different forensic schedule delay methodologies identify delays to the critical path in different ways: similar to Metric and English systems that can both measure distance but do so using different units. Some experts combine two or more delay methodologies in a single analysis to generate a specific result. Akin to combining meters and yards into a single measurement of units even though they are different distances. This paper will identify the situations where using two or more methodologies in a single analysis makes sense or is necessary, and where combining methodologies generates misleading and inaccurate results. The understanding of how different methodologies measure forensic delay differently is a vital component of this discussion, and this paper will explore current understanding of this issue.
CDR-2291 | Contemporaneous Understanding of Criticality: Definitions and Application in Forensic Schedule Analysis | Patrick M. Kelly, PE PSP | 2016 | Contemporaneous understanding of criticality is the project management team’s perception or judgment of the work or issues driving the project’s predicted completion date, as determined by a critical path derived from an adequately developed and maintained series of CPM schedules, and taking into account the limits of their knowledge at the time. Though not usually defined as its own concept, contemporaneous understanding of criticality already exists in good scheduling practice and in case law surrounding Forensic Schedule Analysis. Grasping contemporaneous understanding of criticality as a concept, and incorporating it into one’s delay analysis, has the potential to differentiate a good analysis from a bad one. This paper will provide a definition of contemporaneous understanding of criticality, discuss the context for contemporaneous understanding of criticality in existing scheduling practices and case law, and describe how the existence or non-existence of a valid contemporaneous understanding of criticality will necessarily drive the analyst’s selection of a method and performance of a delay analysis.
CDR-2305 | Implementing the Half-step Update to Improve Project Schedule Controls | John J. Ciccarelli, PE CCP PSP FAACE; Michael J. Bennink, PE CCP PSP; Brian J. Furniss, PE CFCC PSP | 2016 | Industry publications have addressed steps to technically execute the half-step update and identified basic issues relative to the causes of discrepancies, but none have addressed the significant issues of non-progress revisions to schedule logic and planned durations which alter the update schedule. This paper discusses a new Recommended Practice (“RP”) CDR-03, “Implementing the Half-step Update to Improve Project Schedule Controls.” The goal of RP CDR-03 is to develop guidelines for implementing a project controls process in schedule progress and performance assessment. The guidelines will refer to the half-step update analysis and protocols used predominantly for forensic schedule analysis of project disputes as a means of improving project schedule controls and communication. The goal of RP CDR-03 is to provide recommendations and guidelines for more effective schedule control through use of the half-step principals. This thereby improves a project management team’s understanding of project status, provides project stakeholders with accurate project status and planned forecast reports, and improves the project management team’s ability to assess critical path performance during the project to mitigate or avoid disputes.
CDR-2344 | Of Quantum Shades of Gray - A Dilemma for the Expert Witness | Jeffery L. Ottesen, PE CFCC PSP; Kenji P. Hoshino, CFCC PSP; Greta A. Martin, PE PSP | 2016 | Testifying as an expert witness involves resolving many conflicts, both external and internal. This paper discusses one of the internal conflicts. Conveying objectivity is paramount to maintaining credibility with lawyers, judges and other decision makers. Arguments exist that there is often an implicit understanding between the hiring client and the expert that the expert will find a way to leverage the client’s strong positions, and minimize or negate the weaker ones. Consequently, the expert is often caught in an internal conflict between performing objectively on one hand and meeting the client’s expectations on the other. When does an expert cross the line (assuming it exists) from ‘objectivity’ into unwarranted advocacy? This paper presents one paradigm in effectively dealing with this conflict in a way that allows the practitioner to stay true to the AACE Canon of Ethics.
CDR-2402 | Project Claims Avoidance for Owners | Christopher P. Caddell, PE CCP DRMP; Andrew J. Aston | 2017 | In the management of projects, owners often have to resolve claims with contractors, either from them or against them. Avoiding these claims and the source issues when possible can help minimize the negative impact these disputes have on a project’s return on investment. It is important to know what the common sources of project claims are. Claims avoidance actions start during project development with the selection of an appropriate contracting strategy, the development of contract form, contract negotiations and scenario playing. The claims avoidance work continues through the execution of the work with various techniques, data and documentation, and proper change order management. While claims cannot always be avoided, owners using these recommended practices can minimize the probability of claims and lessen the impact when they do occur.
CDR-2417 | Optimizing the Resolution of Disputes on Construction Projects | Lynn B. Larsen, CFCC | 2017 | This paper briefly summarizes the available options (litigation, mediation, arbitration, and Dispute Review Boards (DRBs)), considers typical contract disputes including actual examples, and concludes that only with DRBs are the results most likely to be a win-win scenario. In the other processes even the prevailing party never recovers all its losses. They are lose-lose processes.
CDR-2451 | Principles of Mediation – Explained with Case Study | Avinash A. Gaikwad | 2017 | Alternative dispute resolution processes (ADR) covers various means of disputes resolution beyond the scope of formal litigation. These processes include negotiation, arbitration, conciliation, mediation, etc. Mediation is a voluntary, non-binding and private dispute resolution process wherein a neutral person helps the parties towards achieving a negotiated settlement. This paper will focus on how the principles of Mediation are applied to achieve desired results while settling a prolongation and disruption claim with the help of case study. It also discusses the various conditions where the Mediation principle can be suitably applied for settling disputes/claims in Construction industry. At the end recommendations will be provided on how this method can be applied under different circumstances to save time and cost for dispute resolution process.
CDR-2452 | Change Happens: Implications on Contract Administration Practice and Policy | Dr. George O. Okere, CCP | 2017 | Even though the evidence shows that almost every project encounters contract changes, practitioners still fail to prepare adequately to administer contract changes effectively. Our understanding of those practices that should occur before, during and after contract changes are encountered is important. Ineffective contract administration is a problem that cost taxpayers money and should be evaluated for possible solutions. The objective of this research was to find ways to improve awareness on pervasive contract changes, evaluate the likelihood of encountering contract changes on a project, and investigate a more systematic approach to administer contract changes. The research approach is an in-depth literature review method and the research gathered, analyzed and synthesized literature and empirical data from other research reports. This research provided a perspective and awareness on contract changes, provided evidence to support the fact that the likelihood of contract changes is high, and it explored key factors that affect effective contract administration. This research showed that contract change is inevitable, should be expected, and properly planned for. The findings from this research have implications on practice and policy and should help reshape how contract changes are administered.
CDR-2495 | Overview of As-Planned versus As-Built Forensic Schedule Analysis: AACE® International Recommended Practice No. 29R-03 Forensic Schedule Analysis MIP 3.1 and 3.2 | Scott A. Galbraith, PE CFCC; Michael T. Siburt, PE CCP PSP; John C. Livengood, Esq. CCP CFCC PSP FAACE | 2017 | As-Planned versus As-Built forensic schedule analysis is a method used to identify and quantify delays and, most importantly, the delays that led to the later-than-planned completion of a project. The intent of this paper is to provide the reader with an overview of As-Planned versus As-Built forensic schedule delay analysis. The Method Implementation Protocols (MIP) for this type of analysis are presented in AACE® International’s (AACE) Recommended Practice No. 29R-03 Forensic Schedule Analysis (RP29R-03), Section 3.1 Observational / Static / Gross (MIP 3.1) and Section 3.2 Observational / Static / Periodic (MIP 3.2). The selection of the schedule delay analysis methodology used for a dispute arising from a particular project ultimately is the responsibility of the schedule analyst. In many situations, the methodology chosen may be based on requirements of the contract between the parties. In other situations, the schedule analyst is free to choose the methodology he or she feels best communicates his or her opinions based on the facts of the dispute and available contemporaneous project documentation. This paper presents information about the procedures associated with MIP 3.1 and MIP 3.2 for consideration by the schedule analyst as may be applicable to the specific dispute at hand.
CDR-2499 | Measured Mile Improvements in Pervasively Disrupted Projects | Dr. Tong Zhao, PE PSP; J. Mark Dungan | 2017 | Proving lost productivity is a challenging task in construction claims, especially in the context of pervasive disruptions and cumulative impacts. Although the measured mile method is generally the most accepted approach to quantify loss of productivity in construction projects, its applicability is often hampered when suitable data is not readily available; further, it is not uncommon that its application is abandoned due to the perceived difficulties in proving similar work, and distinguishing the unimpacted, lightly impacted and heavily impacted work. Yet even in these cases, project specific productivity differential methods based on the measured mile concept, are favored because it compares actual performance of similar work on the same project while minimizing the reliance on the budget. Through case studies, this paper will demonstrate how to combine various techniques to establish a baseline, which would extend the use of the measured mile concept to projects on which the measured mile method may intuitively appear inapplicable.
CDR-2531 | Extension of Time Quantification | Thierry Linares | 2017 | The focus of the paper is based upon the authors experience regarding the contentious aspects of Extension of Time on an international construction contract. The introduction focuses on the analysis of the legal foundation (common law) on which the author’s international contract is based. In addition, a comparison of the usual contractual entitlements, requirements, and bars in major contract forms will be done. The body of the paper will concentrate on demonstrating in a practical manner how the extension of time is executed along three types of methodology: 1. Methodologies for technical analysis and demonstration (based on AACE Recommended Practices (RP) RP 29R-03, RP 52R-06, RP 45R-08, and RP 25R-03). These RP’s support reviews and analysis by type of delay and origin (stand-by, disruption, etc.); 2. Best international practices on project and planning management for preparation of extension of time subjects in an objective to avoid disputes; 3. Cost quantification of the various types of extension of time, with a review of the best international practices and a ranking of them from low to high. As well as a review on how quantification needs to be supported by the time extension, which allows for increased recovery potential. The paper is created from the author’s professional experience, and actual projects construction execution and claims examples are given as highlights.
CDR-2542 | Forensic Schedule Analysis – Critical Path Method - Test & Evaluation Systems | Patrick M. Kelly, PE PSP; Kenji P. Hoshino, CFCC PSP; Michael S. Dennis, CCP; Greta A. Martin, PE PSP | 2017 | In order to evaluate implementation methods described in AACE's Recommended Practices for CPM scheduling and forensic schedule analysis, there is a need for a standard demonstration data set that can act as a common tool for practitioners to demonstrate good practice. This paper makes recommendations for the creation of a Uniform Demonstration Construction Schedule Series (UDCSS), a CPM network model, including a full lifecycle set of updates, which can serve as a standard data set for the demonstration of CPM scheduling concepts, testing of forensic schedule analysis methods, evaluation of scheduling software, and teaching of CPM scheduling, while also serving as an open-source 'sandbox'. The UDCSS will model realistic complexity with a variety of conditions and technical attributes, such as types of relationships, multiple calendars, and activity codes, while also providing flexibility and scalability. Use of the UDCSS would add transparency of practice and provide a familiar and predictable known-state for scientific control.
CDR-2543 | Proposed Format and Content for Subordinate Recommended Practice, 29R-03-3.X | Kenji P. Hoshino, CFCC PSP; Michael S. Dennis, CCP; Greta A. Martin, PE PSP | 2017 | This paper is an effort to reach a consensus on the standard format and an inventory of contents for a series of Subsidiary Recommended Practice documents outlining in detail each of the nine method implementation protocols contained in Recommended Practice 29R-03, Revision 2. The purpose is to alleviate the frequency and complexity of revisions to the Master 29R-03 document as revisions become necessary to one or more of the nine methods currently outlined in 29R-03. This will also reduce the bulk of 29R-03 from 134 pages to a size that matches the rest of the RP's in AACE’s® library. The paper will use Method Implementation Protocol 3.8 as a mock topic to discuss the requisite contents of the Subsidiary Recommended Practice.
CDR-2568 | What’s in a Name? – Forensic Delay Methodologies | Roger R. Nelson, PE; Bernard Ong | 2017 | Forensic schedule delay practitioners seem to be in the midst of a contest to invent new names for familiar forensic schedule delay methodologies. Despite the publication of AACE® RP No. 29R-03 in 2007, the number of new names for similar, if not identical methodologies, has grown – and continues to grow. Furthermore, it’s unclear if a consensus among practitioners has been made on the names of the more frequently referenced methodologies. In the past decade since the publication of AACE® RP No. 29R-03, books, articles, and methodological guides have been published that rename familiar methodologies and occasionally try to repackage them into substantively different methodologies. For example, the UK-based Society of Construction Law Delay and Disruption Protocol has identified two methods of “Windows.” One appears to be a Contemporaneous Period Analysis (MIP 3.3) and the other seems to be an As-Planned vs. As-Built (MIP 3.2). This paper surveys publications and journals in an effort to make sense of the nomenclature and identify consensus - if any. Methodologies described in the sources are inventoried by name, and categorized into the system developed in AACE® RP No. 29R-03, or if appropriate, into new categories.
CDR-2608 | Hot Tubs and Other ADR Remedies for Disputes that Ail You | Kathleen Olden Barnes; Christopher J. Brasco; George "Trip" Stewart | 2017 | The prompt resolution of claims is more essential than ever on the modern construction process. The speed, frequency, and complexity of changes as well as the conditional availability of project financing have linked project success and efficient claim resolution more closely than they have ever been in the past. This paper explores how expert-based approaches to ADR can be tailored to facilitate claims resolution on even the most troubled projects. By effectively integrating subject matter experts into the ADR process, parties may be able to resolve issues on complex construction projects more quickly and efficiently. Accordingly, this paper will address concurrent expert testimony, also known as “hot tubbing,” and how this process helps foster expert-based ADR. This paper will then proceed to explore how hot tubbing may be modified so that it better fits the needs of the dispute at hand.
CDR-2616 | Global Construction Disputes Report 2016 - Don't Get Left Behind | Roy Cooper, PE; Brian Goodreau, PSP | 2017 | The Global Disputes Report presents an in-depth, data driven review of projects and disputes globally in 2015. The report focused on five key areas: the length of disputes, average value, common causes, most popular resolution methods and region specific nuances. This report also includes an overview of the macroeconomic market position and goes on to cover several global regions, including North America, UK, Continental Europe, Middle East, Asia, and Australia. This paper reveals key themes and insights into the global construction disputes market. Any dispute is case specific, so to endeavor to group causes and develop averages can risk omitting critical information related to the overall nature of the dispute. However, given the range and depth of the coverage, dispute trends, both globally and regionally, are indicative of market trends. The results show that disputes globally have marginally reduced, but the durations have markedly increased. The increased length of disputes will have multiple effects for both parties and are likely to, ultimately, have a negative impact on the construction industry.
CDR-2620 | Top Pick, The Contemporaneous Period Analysis - Split Methodology Forensic Delay, MIP 3.4 | Mark F. Nagata, PSP; Christopher W. Carson, CEP DRMP PSP FAACE | 2017 | The Contemporaneous Period Analysis - Split methodology (Method Implementation Protocol 3.4) is used when a schedule update has been performed based on progress, but schedule modifications have also been made before the schedule is published or submitted. When evaluating liability for delays (and damages related to acceleration) it is necessary to properly assign the project delay to the responsible critical work activities, events, or schedule revisions. This methodology splits the analysis of delays between progress and schedule revisions so each can be evaluated separately, and allows identification and monitoring of lessons learned from forensic analysis such as re-planning failures and erosion of vital float through casual mitigation efforts. This paper will discuss the steps in this process, provide examples of how the method works, and discuss the evaluation of the results.
CDR-2662 | RP29R-03 MIP3.5 Observational / Dynamic / Modified or Recreated | Walied Abdeldayem; Mark C. Sanders, PE CCP CFCC PSP | 2017 | Windows Analysis is a term that has been used (and misused) frequently to refer to various, and in many situations very different, delay analysis methodologies. Other papers under the FSA series, related to this paper, address various implementations and derivatives of analysis methods that utilize the windows analysis approach. This paper focuses on the usage of modified and/or recreated schedules, mostly after the fact, as a tool to analyze delays. The paper explains the various derivatives of this method, discusses their strengths and weaknesses and addresses the challenges that may face an analyst in carrying out this type of analysis. Further, the paper provides useful recommendations to assist the analyst in deciding whether this method is suitable for the case at hand and outlines the objectives and expectations when using this method.
CDR-2684 | An Insight to Concurrent Delay Analysis | Devdas Tamboli, CCP PSP; Manoj Joshi | 2017 | Concurrent delays are quite common in construction projects, however definition and understanding of concurrent delays is still a matter of confusion. How concurrent delays are analyzed plays an important role in their quantification eeand compensation. Construction contracts often don’t specify how to deal with concurrent delays and this creates confusion. General understanding about concurrent delays is, two delays happening at the same time time. However, some recent theories conclude that, concurrent, delays need not necessarily take place at the same time. Understanding and analysis of concurrent delays not occurring at the same time is an intricate subject. The paper focuses on explaining different types of concurrent delays in construction projects, factors affecting analysis of concurrent delays and analysis of concurrent delays using window analysis and but for analysis.
CDR-2708 | Top Pick, The Collapsed As-Built Windows Schedule Analysis Method | Andrew Avalon, PE PSP; Ronald J. Rider | 2017 | The Collapsed As-Built Windows Schedule Analysis (AACE® International Recommended Practice 29R-03, Method Implementation Protocol 3.9) is a modeled, subtractive, multiple-base method. It is a retrospective CPM schedule analysis which is typically used to prove entitlement for compensable delay and assess concurrency of delay within a window of time. The analysis simulates the as-built conditions within a schedule window and then delays are removed from the CPM model. If the forecasted project finish date “collapses” but-for or absent compensable delays, then entitlement for compensable time-related costs can be demonstrated. This paper addresses the usage of the Collapsed As-Built Windows protocol and the advantages and disadvantages of the methodology.