## Sheet1
ID | Title | Authors | Year | Description
PS-3597 | Practical Planning and Scheduling for Capital Project Delivery in the Pharmaceutical Industry | Francisco Cruz Moreno, PE | 2021 | Initiating a pharmaceutical capital project requires a deep understanding of the unique processes related to current good manufacturing practices, along with experience in the design, procurement, construction, commissioning, qualification, and validation of facilities, utilities, and equipment. Additionally, planning should account for the regulatory affairs that approve bringing a product to market in this highly regulated industry. While most of the pharmaceutical capital projects are schedule-driven in a first-to-market business model, improper planning and delays constantly jeopardize the release of new products. This paper describes practical techniques to plan and schedule new construction and renovations of existing buildings; typical sequences and durations used for commissioning, qualification, and validation activities; timing for engagement with different stakeholders; common pharmaceutical terminology employed during all phases of a project; and recommended approaches to leverage previously performed work to potentially gain time in the project schedule. Novice and seasoned practitioners alike will benefit from following these procedures. The author has successfully used these practices in manufacturing facilities for oral, parenteral, and topical administration products located in the Americas, Europe, and Asia.
PS-3608 | Schedule Beta: A Financial Tool to Evaluate Project Schedule Performance by Analogy to CAPM Approach | Brahim Seddiki, CCP | 2021 | The earned value metric schedule performance index (SPI) has limitations in describing a project’s schedule performance and variances. A new research study conducted by Construction Industry Institute (CII) has suggested augmenting SPI with a new way of evaluating and assessing performance. Schedule beta (𝛽) originates from stock performance index in finance and has a potential to become a new standard of measuring performance and quantifying systematic and specific risk in a project’s duration-based metrics. This technical paper will demonstrate a mathematical formulation and will exhibit the practicality of applying schedule beta to determine a project’s duration-based risk or opportunity. A brief introduction, and highlights of the original theory of capital asset pricing model (CAPM) developed in the sixties by Sharp, Lintner and Black, Fischer, Jensen and Scholes will be presented. The theory will then be customized and applied to a sample project for the purpose of investigating that project’s risks and measuring its performance versus other projects in a portfolio.
PS-3616 | A Planning and Scheduling System for Successful Project Delivery: A Case Study | Jonathan R. Hunt; Hannah E. Schumacher, PSP FAACE | 2021 | To deliver projects on time, one must have a reliable and predictable project schedule that is developed with input of all parties, frequently updated throughout the course of the project, and is used as a tool by the project team and all stakeholders to manage the project. While it is important to have knowledge of how to use scheduling software, it is even more important to have a thorough understanding of the best practices of planning and scheduling. This paper outlines best practices to implement a successful scheduling program. In this paper the authors will describe their company’s scheduling management process for developing and managing schedules for successful project delivery. They will describe their guidelines and training programs that help project team members successfully plan, manage, and communicate their schedules.
PS-3642 | Scheduling Metrics and the Dangers of Remaining Silent | Beatrice Nasui; Ronald M. Winter, PSP FAACE | 2021 | Software makes it simple to identify and count particular aspects of CPM schedules in what is known as “schedule metrics”. Some companies and governmental agencies have already implemented systems to measure the schedule quality using their selected metrics, with predefined thresholds. As such, multiple guidelines have made their way into the project controls industry, but most of them have been declared by fiat, not community consensus. Soon they will be considered industry standards, even without input from the users. But are the right aspects of schedules being evaluated or just the easy ones to measure? And what message do these metrics convey? The application of a “one size fits all” quality criteria ignores the fact thresholds are impacted by a variety of factors. Are commercially proprietary measurements becoming required industry standards without proper consultation? The project controls community should become involved in setting the standards that they will be using. This paper highlights the dangers of remaining silent when others are defining the schedule quality by mere convenience than community acceptance. It could serve as basis for a future RP on the subject.
PS-3643 | Owner Project Scheduling during the $6B Dulles Corridor Metrorail Project | Matt Marzilli, PSP; Mike P. Ryan, PE PSP | 2021 | goal of every project is to complete the work on-time and on-budget. While often undervalued, the owner has an essential role in the development and maintenance of the project’s critical path method (CPM) schedule. Written by the schedulers for the Metropolitan Washington Airports Authority on Phase 2 of the $6B Dulles Corridor Metrorail Project, this paper shares the lessons learned during this fast-paced, exciting project. Questions answered include: What are the best ways to explain the critical and near-critical paths of a complex schedule to non-schedulers? How can one effectively distill a 40,000-activity schedule into layouts that the owner’s on-site management team can actually use? What non-CPM schedule tools can be used to better illustrate the plan and track progress? A successful scheduler must fully understand the contract and be able to coordinate with team members from different disciplines, regardless of the project’s size. This project provides an excellent case study on real-time scheduling and project management on a US-based megaproject. The lessons learned can be applied to other large-scale transit projects across the world.
PS-3648 | Getting Back to Basics: Update Schedule Review by the Numbers (Recommended Practice Numbers, that is) | Marina G. Sominsky, PSP; Ronald M. Winter, PSP FAACE; Katherine Baron | 2021 | Performing an update schedule review submitted by a 3rd party requires a vastly different skill sets than that of creating a schedule. The scheduler who creates a schedule works with a large number of construction professionals who will provide feedback and guidance. Typically, the scheduler who reviews a 3rd party's schedule submittal works alone. This process can be quite daunting for the first-time reviewer. The reviewer does not need to work alone as long as there is an access to AACE's incredible library of recommended practices and technical papers. This paper focuses on the key documents that aid in determining the main topics of the review memorandum, assist in identifying the culprits that make schedule updates non-compliant, as well as provide solid guidelines on how to gauge schedule's overall quality. The authors hope to inspire and motivate project controls professionals to advance their skill set from being a proficient scheduler to becoming a trusted scheduling consultant.
PS-3715 | Paper or Plastic? Microsoft Project versus Oracle Primavera P6 | Charlie Jackson, PSP; Hannah E. Schumacher, PSP FAACE | 2021 | Selecting the appropriate scheduling software to be used for a project is one of the key decisions that must be made prior to the start of the project. The choice of scheduling software is often dictated by contract documents or by the contractor’s company standards and guidelines. Regardless of the selection process, the scheduler is going to be ‘stuck’ with this decision for a long time and he/she needs to realize how this decision affects the development and management of the project schedule. It is important to understand the features, benefits, and limitations of using the selected scheduling software. In this paper, the authors examine two of the leading scheduling software tools that they regularly use on real construction projects: Microsoft Project Standard and Oracle Primavera P6 Professional. The authors explain the details on how these software packages may best be utilized for scheduling construction projects and programs.
PS-3742 | Schedule Effectiveness versus Specification Compliance, Which Should Prevail? | Gayathri Shetty; Adam S. Lackey; Robert M. Freas, PSP | 2021 | When projects are affected by unexpected or as-built events such as unforeseen conditions, design errors and/or omissions, or owner requested changes, the contractor’s baseline schedule and execution plan are not typically realized. Industry recognized authorities recommend that project schedules be regularly updated with two purposes in mind: reflect the current status of the project and keep the schedule as an effective management tool. These objectives can be at odds with project specifications that prohibit revisions to the schedule unless approved by the owner. If the schedule is not kept current, does the schedule become obsolete and nothing more than a payment application tool? This paper will present an in-depth discussion of why the contractor should be permitted to keep the schedule current and the problems that result from this prohibition, as well as the owner’s perspective of not allowing the contractor to revise the schedule to include as-built events occurring during project execution. Possible risks that the parties can be exposed to in these situations will also be identified and discussed. Finally, this paper will present proposed solutions for the parties to consider, which attempt to satisfy the specification requirements and keep the schedule as an effective management tool.
PS-3769 | Implementing the Half-Step Analysis During Your Project – The “Devil” is in the Details (Half-Step Analysis Phase III) | Matthew G. Nichols, PSP; Brian J. Furniss, PE CFCC PSP | 2021 | The half-step analysis method segregates and quantifies schedule progress and revisions on an update-by-update basis. The power of the method lies in the ability to assess the performance of a plan (progress) and how that plan changed (revisions) over project time, providing a unique understanding of a project’s evolution. For example, a project milestone could be losing progress on a monthly basis, yet the project milestone could appear to be making as-expected progress if the contractor minimized the progress loss by revising the remaining schedule activities. Two prior Technical Papers, CDR.2305 and PS.2491, provided macro-level examples of how this method could be used to better understand a project both during and after its completion. This paper will explain how to perform a half-step analysis using Primavera P6 in a step-by-step fashion and using clear graphics. The process to complete the half-step analysis is simple; however, there are options and steps that must be followed to ensure an accurate bifurcation result. As with most successful analyses, the “devil” is in the details. After demonstrating how to progress a schedule, the paper will also demonstrate how to analyze schedule revisions, and more importantly, critical schedule revisions. Finally, the paper will cover real-life applications of the half-step analysis on multiple projects, both for a monthly schedule review and a forensic schedule analysis.
PS-3794 | The Art of Scheduling | Sylvia M. Donado | 2022 | With every discipline, foundational concepts are instilled and continually used and developed in order to reach advanced levels. These relate to a core set of technical principles and aspects of a particular craft. In mastering the technical aspects and continually refining those skills, an individual can learn to use those rules in their own way in order to give the work stronger meaning and effectiveness. This same thought process applies to the arts as well as the sciences. In today’s complex climate, everything has become segmented where technical and creative skills are seen as separate skillsets yet they both have significant value in managing projects. The manner in which technical skills get applied is what leads to effectively developed schedules and management of CPM schedules in order to effectively manage and control projects. Proper CPM techniques have proven to be extremely effective in establishing a communication of a plan, establishing production goals, monitoring and managing progress, and managing change in projects and programs.
PS-3804 | The Top Ten Worst Situations With Proven Project Controls Solutions | Christopher W. Carson, CEP DRMP PSP FAACE; Glen R. Palmer, CFCC PSP FAACE | 2022 | Many situations occur in project delivery which appear to be unmanageable or impossible to resolve, and the authors have a long history of experience in successfully pulling off resolution of what appear to be impossible or very difficult situations. These situations range from project problems that arise from owner or contractor actions or inactions, or even third-party interference, and risk negative impacts to the project goals. Some of these were projects where the authors were brought in after the CM team recognized that they were in trouble, and some were projects that the authors participated as team members and provided the solutions. Participants in this session will benefit from being provided ten good war stories about difficult situations and learning about proven practical solutions that should give them insight into resolving similar issues in their own careers. These are not hypothetical solutions but rather actual issues and solutions that were implemented to successfully resolve real problems. The authors have classified these situations so they can serve as a library of typical types of project issues with solid and workable solutions.
PS-3805 | Scheduling: Do You Have All the Puzzle Pieces? | John M. Holincheck; Sylvia M. Donado | 2022 | Projects are becoming more complex and costly requiring a greater level of attention to the management of both time and resources. Critical path method and other scheduling concepts, tools, and techniques are applicable to most industries that rely on planning and scheduling professionals to effectively manage work. Ensuring all components are considered thoroughly during the planning and scheduling of the project can be a factor between overall project failure or success. Current market climate requires a more intricate level of detail. However, the segmented nature of managing the work creates communication and knowledge gaps that result in things being missed during the planning process. Making sure all components are considered from the beginning of the project can ensure a more successful execution, as well as monitoring & controlling the work throughout the project lifecycle.
PS-3835 | Critical Path Method (CPM) and Project Production Planning (PP): Complimentary or Exclusionary? | Richard H. Stack, Jr.; Albert P. (Mac) McMillan | 2022 | The Project Production Institute (PPI) held a webinar in October 2020 titled “Does CPM Scheduling work?” Basic premise was that CPM had failed to deliver projects on schedule. PPI recommends abandoning CPM scheduling and applying production planning (PP) techniques, developed for manufacturing, to construction projects. PPI recommended having only a Level 1 Master Schedule for management reporting. This is a very bold recommendation by PPI. There is no argument that mega projects (>$1 billion USD) have performed terribly for years on both cost and schedule. CPM has been used to manage most of these project schedules. But is CPM the cause of the failures? This presentation assesses the merits of both CPM and PPI process to determine: • Why has CPM not been effective on mega projects? • Can CPM be “fixed”? • How can CPM successfully manage large construction projects? • Are CPM and PP complimentary or exclusionary?
PS-3850 | Utilizing Agile Work Methods in the Schedule Development Process | Abbas Shakourifar, PSP | 2022 | Schedule development is one of the primary areas in the project management process. Project teams focus on gathering data and developing their schedules from the early phase of each project. A well-developed CPM schedule is a key to success for every project team. This paper identifies the characteristics of the schedule development process which make it a proper use case for agile work methods. Also, it explains how key schedule statistics and critical path metrics can be used as key performance indicators (KPI) during agile schedule development to improve and optimize the project schedule throughout the process. This is to ensure that the final product is a robust and reliable schedule that can be used for both monitoring of the project and forecasting the end date.
PS-3854 | Planning and Building a New Arena Under an Existing Roof | Zachary A. Hallstrom, PSP | 2022 | The purpose of this paper is to highlight the creative and effective planning and scheduling tools used during the construction of Climate Pledge Arena in Seattle, WA. The mass excavation of over 700,000 CY of material was planned and executed while supporting an existing, historic roof structure weighing over 44,000,000 lbs. Phased completion of the excavation allowed new foundation and structural elements to be installed until the existing roof was fully supported by the new structure, thus allowing the temporary supports to be removed. The project team used a detailed CPM schedule, LEAN techniques including weekly work planning, 4D scheduling, resource loaded schedules, and other techniques to plan work safely and effectively. This paper and presentation will highlight the successes and lessons learned of an extremely complex and unique project.
PS-3856 | Applying Multiple Calendars in a Projects Schedule – Peace of Mind, or Source of Concern? | Saeid Khademagha, P.Eng. PSP | 2022 | Calendars and the accurate utilization of them is one of the most important subjects to the success of a project schedule. Due to the variety of environmental and non-environmental restrictions in most of the large-scale and complex construction projects (i.e., in-water work restrictions, road or track closures, winter shutdown, resource availability, night shift work), defining and applying multiple calendars with different allowable working days and working hours representing these restrictions is a necessity. Although schedules using multiple calendars is a generally accepted practice (even required in some cases), different calendars do not always work well together and in some cases provide dilemmas. While multiple calendars may offer peace of mind, in some cases can negatively impact the project schedule indexes and become a source of concern. Some of the negative impacts and effects of utilizing multiple calendars in the project schedules are discussed using several real case study projects. Approaches for preventing or mitigating such negative impacts and effects are also presented.
PS-3866 | (Presentation Only) Is it Time to Switch from P6: An Unfiltered Review of Oracle Primavera Cloud | Jeffrey Milo, PSP; Christian Velasco | 2022 | Hate sitting through software presentations where they tell you what it does but never show you the software used in actual real life situations? Curious to really see Oracles new scheduling tool? This is the presentation for you. Jeffrey Milo, Senior Scheduling Manager at Landmark Construction, has been using Oracle’s new scheduling tool Primavera Cloud since April of 2019. Through his involvement in Oracles Early Adopter program he has had unprecedented access to both the software and its developers. In this presentation he will take you on an all access tour of the first scheduling program built by Primavera from the ground up since P3, show you actual schedules built in the software and explain how Landmark Construction uses the tool every day. He will also give an unfiltered review of the software’s strengths and shortcomings in comparison to Primavera P6.
PS-3897 | (Presentation Only) Two Truths and a Lie Game - Fellows Edition | Christopher W. Carson, CEP DRMP PSP FAACE; Ronald M. Winter, PSP FAACE; Glen R. Palmer, CFCC PSP FAACE; Kenji P. Hoshino, CFCC PSP FAACE; John J. Ciccarelli, PE CCP PSP FAACE | 2022 | The AACE Fellows have hundreds of years worth of experience in all the cost engineering/project controls disciplines, and this session is an opportunity for Fellows to give back to the community. This year the war stories will all follow a theme of “Recovery and Mitigation Efforts that Went South”. The session will include a Moderator (Carson), three Storytellers (Palmer, Hoshino, Ciccarelli), and a Doubter (Winter), all AACE Fellows. The three Storytellers will each provide three short war stories from their past projects, each of which will include two truths and one lie in their mix of stories, and the Doubter will question each Storyteller and provide challenges and objections in an effort to prove the stories to be lies while the Storytellers defend their stories. Then the audience will get a chance to ask follow-up questions and subsequently vote on whether the story is a truth or a lie. In the past, the Storytellers had trouble coming up with lies that were more extreme than the truths, so the audience eventually just correctly voted "true" on all stories. The Storytellers were chosen this year specifically for their ability to come up with lies as unbelievable as the truths. Come armed with your lie detectors working.
PS-3964 | (Panel Discussion) Two Truths and a Lie Game - Fellows Edition | Christopher W. Carson, CEP DRMP PSP FAACE; Ronald M. Winter, PSP FAACE; Glen R. Palmer, CFCC PSP FAACE; Kenji P. Hoshino, CFCC PSP FAACE; John J. Ciccarelli, PE CCP PSP FAACE | 2023 | The AACE Fellows have hundreds of years' worth of experience in all the cost engineering/project controls disciplines, and this session is an opportunity for Fellows to give back to the community. This year the war stories will all follow a theme of "projects pulled back from the brink of disaster".The session will include a moderator (Carson), three storytellers (Palmer, Hoshino, Ciccarelli), and a doubter (Winter), all AACE Fellows. The three storytellers will each provide three short war stories from their past projects, each of which will include two truths and one lie in their mix of stories, and the doubter will question each storyteller and provide challenges and objections in an effort to prove the stories to be lies while the storytellers defend their story. Then the audience will get a chance to ask follow-up questions and subsequently vote on whether the story is a truth or a lie.
PS-3986 | A Proposal for a Standardized Set of Definitions of Work Availability | Michael A. Mac Guinness, C.Eng. | 2023 | Work availability is a frequent topic of discussion when it becomes necessary to resolve challenges resulting from unforeseen events. Nevertheless, there is no agreed definition of it, and without definition, there is no way to consistently quantify it. In practice, concepts of work availability are remarkably fluid. They vary according to the time scale considered, the effect of work sequence, and the assessment of multiple other factors. In its most expansive definition, work availability can be considered “all work for which IFC drawings have been issued minus completed work.” At the other extreme, this definition could be limited to “work for which all necessary prerequisites including but not limited to labor, material, permits, etc., are complete and ready at site for installation.” It is not unusual for owners and contractors to have heated disagreements regarding work availability due to unrecognized differences in their concept of it. A set of definitions is proposed that reflects the stages of preparation of work as its prerequisites are completed before its scheduled dates, and as it progresses through the medium- and short-term planning process. A simple system dynamics model is used to dynamically quantify and to illustrate graphically the quantity of work in each stage, how that changes over time, and how expectations for work availability influence manpower planning and mobilization.
PS-3990 | Managing the Master Schedule for Multi-Prime Contracts | Pirouz Bozorgnia, PSP; Ibrahim Odeh; Weijia Chen | 2023 | Multi-prime contract is a procurement model where the owner is directly entering into a contract with a number of different trades to complete a program. The model allows the owner more control over each work element but places an additional burden on the owner to manage and coordinate all of its trades. This would require a sophisticated master schedule aligned with each trade's plan to complete the work and identification of potential risks as the project develops. This paper provides recommendations on developing a baseline master schedule, utilizing project documents to analyze resources and identify risks, as well as recommendations regarding the contract schedule language that will not be overly burdensome on the trade and would still protect the owner from coordination claims as they arise throughout the project.
PS-4018 | Benefits and Applications of Half-Step Scheduling | Joao Paulo Matos Dias, PSP; Loami Cabral | 2023 | With the increased demand and complexity of construction projects, where the investments and risks are high and deadlines are tight, there is a need for innovative and accurate project planning and scheduling approaches and processes to be adopted. Having these processes well-structured and implemented throughout the project life cycle will guarantee feasible and transparent information, and will act as a mechanism of predictability with a direct impact on the contractual management and delivery performance. Through an accurate study of the application of half-step scheduling techniques, this technical paper aims to suggest alternatives to optimize the periodical prospective schedule updates and management of risks associated with the creation of half-step schedules, in addition to presenting the direct benefits of their tailoring, both in adherence to the AACE International's Recommended Practice for Forensic Schedule Analysis (RP 29R-03) and in possible reductions in implicit limitations, such as concurrency and performance problems.
PS-4021 | How to Save a Troubled Project: Case Studies of Transitioning to Takt Planning | A. Keith Rines, PE PSP | 2023 | How does one shift the culture of a troubled construction project to complete on time when the project schedule is forecasting late completion? Takt planning is a scheduling tool which can do just that by paying careful attention to balancing workflow and utilizing space as a resource. The purpose of this paper is to identify schedule variances and minimize impacts by focusing on flow. This paper will explore challenges from implementing a workforce management plan during construction when the project was delayed and executed with poor original planning and an incomplete critical path method schedule. This paper will apply the multiple lessons learned from one case study to a second case study. Takt planning is a practical application of executing a collaborative endeavor involving owner, contractor, and subcontractors to switch everyone’s thinking from push to pull planning for better project outcomes. Construction is dynamic and the project planning needs continuous adjustment to mitigate delay and avoid chaos.
PS-4042 | Extending Your CPM Schedules to Embrace the Power of Linear Scheduling | Santosh Bhat, PSP; Christopher W. Carson, CEP DRMP PSP FAACE | 2023 | Projects that are performed in a linear fashion, such as the construction of tunnels, railways, highways, pipelines, and transmission networks are becoming increasingly complex and face greater constraints in achieving their desired delivery outcomes. The planning and scheduling of such projects is also increasing in complexity and whilst most of these projects rely on CPM schedules for time management, the benefits of improved schedule communication, analysis, and stakeholder buy-in offered by linear schedules are still relatively under-utilized. Linear schedules are a visual method of representing schedules for such projects. They offer additional benefits beyond traditional Gantt chart outputs and can be easily understood by a wider audience of project stakeholders. This paper will provide an overview of linear schedules, the benefits offered by using them on linear projects and also discuss techniques and considerations of appending additional data to CPM schedules to produce linear schedules. Further use cases such as delay and disruption analyses of project schedules will also be discussed.
PS-4044 | Integrating Sustainability Metrics with CPM Schedules: A Novel Approach with Applications in the Construction Industry | Dr. Achintyamugdha S. Sharma; Dr. Priyanka Deka; Goutam Jois, Esq.; Umesh K. Jois | 2023 | This paper describes a novel way to integrate sustainability metrics into a critical path method (CPM) based project schedule. To date, common industry practices of project controls do not include quantification and monitoring of environmental emissions associated with projects. This research team has addressed this gap by developing a method of estimating 100-year global warming potential (GWP) CO2-equivalent emissions associated with each activity of a CPM schedule. This methodology will transform a CPM schedule into a holistic tool, which can be used by project owners, contractors, construction managers, and other stakeholders to make meaningful decisions on the basis of duration, resources, cost and GWP emissions. This novel technique can be applied on virtually any type of project, including residential and commercial buildings, special purpose construction (such as data centers), power/utilities, infrastructure projects (highways/railways, bridges, aviation, transit facility buildings, etc.), signals and communication systems, and more, as exemplified through a few fictitious examples in this paper. Additionally, the paper describes (1) potential relationships between GWP, and resources and cost as well as (2) the impacts of delays and change orders on GWP emissions.
PS-4061 | Past Performance Can Be a Good Indicator of Future Results | Tara L. Hannebaum; William C. Schwartzkopf | 2023 | Normal scheduling practice on construction projects to determine if a project has gained or lost time during the update period is to update the schedule with actual progress, calculate the schedule and compare the forecast completion date to both the forecast completion date in the prior update and the required completion date. That process can—and often does—provide misleading information. Looking only at the forecast work to the right of the data date ignores an important source of critical information. Comparing actual progress to planned progress during the update period provides significant insight into whether the project is actually gaining or losing compared to the schedule. When actual losses during a schedule update are immediately “offset” or mitigated by changes to durations or logic of future work, the project end date does not move, and no loss is assigned in the period. Mitigating delays to maintain and achieve on-time performance is a worthy goal, but when it simply makes a project appear to be on schedule when it may not be, it can: • Cause problems for the owner who discovers after it is too late to adjust that the project will finish later than planned • Require the contractor at the end of the project to accelerate work at great cost to meet the unrealistic end date created by the mitigation This paper discusses an analysis method that addresses this situation and allows for a proper analysis of actual critical path delay and realized mitigation independent of predicted future critical path performance.
PS-4070 | Identifying and Understanding Schedule Revisions using Basic Primavera Software | Matthew Marzilli, PSP; Michael P. Ryan, PE PSP | 2023 | Identifying and understanding impacts due to revisions is an important part of the schedule review or forensic analysis process. Especially on larger projects, it can be a struggle just to organize and tabulate the hundreds of revisions made to each update without the use of external software. This paper will first explain how to find and organize schedule revisions using the tools available in Primavera P6. Next, it will examine some of the lessons learned during the analysis of revisions on dozens of previous projects. Finally, using case studies from past projects, it will illustrate how identification of the impacts due to these revisions improved the schedule review or forensic analysis process.
PS-4097 | Float Enabled Resource Envelope: A New Tool for Resource Management | Kenji P. Hoshino, CFCC PSP FAACE; Richard J. Wood; Steinar Dalva | 2023 | Standard CPM calculation provides two extreme performance scenarios: the early start, which uses no float, and the late start which uses all the float. Most real-world implementations use some float. The use of float and the extent of its use is unpredictable because it is subject to the circumstances and the conditions of the project, which are driven by many factors. Therefore, the supply of necessary resources for implementing the schedule must anticipate all the possibilities of float usage. A resource histogram that reflects this reality must be based on an adequate sampling of many float-usage scenarios and be composited from data-points gathered from the scenarios for each period on the histogram timescale. The paper will introduce a new computational tool that seeks to explore this relatively untapped reserve of resource management.
PS-4126 | Changing Schedule Performance Index Methodology | Kareem M. Khattab, PSP | 2023 | One of the frequently used indexes in the industry is the schedule performance index (SPI), which is calculated by dividing the earned value (EV) over the planned value (PV). As the total earned value equals to the total planned value so the SPI will always tend to 1 at the project completion regardless of the schedule status. The schedule may be delayed and still the SPI is showing tendency to 1. Moreover, SPI can show a value greater than 1, while the schedule is delayed. This happens when the non-critical activities are ahead the planned dates, and its’ value exceeds the values of the critical activities values which are delayed so earned value exceeds the planned value and SPI is greater than 1. SPI may also show a value of less than 1, and the schedule is ahead, this would be the case if the critical activities are ahead, and the non-critical activities values exceed the critical activities and are behind. To overcome these main SPI fallbacks, this paper and presentation introduces new terminologies, metrics, equations, and indexes for measuring the schedule performance which can be utilized and used for corrective actions for the delayed activities and preventive actions for the future activities.
PS-4127 | Application of Linear Schedules in Project Validation and Forensic Analysis | Aldo D. Mattos, CCP PSP FAACE | 2023 | Time-location schedules, also known as linear schedules, have been regularly used to plan repetitive and/or rectilinear projects, due to their ability to show the activities along the time in a more visual and concise way. However, many planners don't exploit the full capacity of time-location schedules. In this paper the author shows some applications and benefits of time-location schedules in project validation and forensic analysis: (i) consolidation of information; (ii) schedule validation; (iii) progress monitoring; and (iv) tool for forensic schedule analysis.
PS-4131 | The Value of Total Float Values in Schedule Analysis: Ensuring and Restoring the Integrity of Schedule Float Values | Saeid Khademagha, P.Eng. PSP | 2023 | From the moment a project is scheduled until it is finished, one phrase—"critical path", is consistently conveyed in all project meetings at various levels. This phrase is the essence of the critical path method (CPM) as the most widely used and accepted planning and scheduling method. Since the total float values define the criticality and near-criticality of the activities, or in other words, the flexibility within a schedule, any action that has a detrimental impact on the validity of the total float values may cause some activities to mistakenly appear critical. This inaccurate result may mislead the project management team into making wrong decisions for the remainder of the project, which could violate the contractual completion date of the project. Incorrect logic, missing activities, multiple calendars, out-of-sequence progress, and time constraints all may result in discordance and confusion in total float values, and consequently, a meaningless critical path. In addition to resulting in inaccurate time management for the remainder of the project, these flaws in total float values can also undermine the accuracy of resource management, risk management, and delay analysis. It is essential for the project management team, including the planner and schedulers, to professionally know how to identify inaccurate and meaningless total float values and to fix them in a proper and professional way. The negative impacts and recommended resolving practices will be described in this article through the discussion of several actual case study large-scale schedules.
PS-4151 | Advanced CPM Milestone Review | Ronald M. Winter, PSP FAACE | 2023 | Several AACE recommended practices (RP) mention that the scheduler should specifically consider milestones in the creation and review of the typical construction schedule. These RPs do not detail what should be considered when reviewing milestones. It is not enough for the scheduler to look at them and hope that something ‘pops-out’. Advanced schedulers should focus on a list of specific topics. This paper discusses the hows and whys of the proper use of milestones in CPM schedules and how to make better schedules. From baseline schedules to schedule updates, this handy guide gives advanced schedulers more tools to ensure that they have better schedules and better run projects.
PS-4157 | Scheduling Requirements Across the U.S. Federal Government: Summary and Recommendations | Michael R. Nosbisch, CCP PSP FAACE; Diane Bragoni, PSP | 2023 | This paper will summarize and advise on the practical applications of current scheduling requirements across the federal government of the United States of America, encompassing both construction projects and aerospace programs. Federal projects/programs have their own unique project management and controls requirements compared to the private sector. These requirements may catch contractors off-guard if they were not fully reviewed or understood prior to contract award. For example, on large aerospace programs, usually developed under cost reimbursable contracts, control account-level detail is often required to roll up to an overall integrated master schedule (IMS) as a key element of an earned value management system (EVMS). Additionally, federal construction projects administered under the standard Unified Facilities Guide Specifications (UFGS) 01 32 01.00 10 scheduling specifications require schedules to be cost loaded, balanced per the contract line item numbers (CLINs), and converted into a Standard Data Exchange Format (SDEF) file that can be uploaded into the government’s system for review and payment processing. This paper will provide an understanding and awareness of the unique scheduling specifications/guides and associated requirements across multiple federal agencies. The authors will also leverage their own personal experience in providing recommendations to better prepare readers to successfully navigate them in support of their projects/programs, regardless of scope.
PS-4230 | Schedule Narratives and Reports | Delbert E. Bearden, PSP | 2024 | Effective communication of project schedules is pivotal to the success of construction and engineering projects. In response to the increasing complexity of these projects, this paper provides comprehensive guidance tailored to professionals responsible for developing influential schedule narratives and reports. The paper delves into the purpose and scope, emphasizing the role of effective communication, collaboration, and understanding among project stakeholders. The objective is to develop schedule narratives and reports that contribute significantly to project success. Covering critical aspects such as project milestones, progress updates, risk mitigation strategies, resource allocation, and more, this paper seeks to enhance the quality and effectiveness of schedule documentation. By equipping project professionals with the tools and knowledge to create impactful schedule narratives and reports, the paper aims to positively influence project outcomes, assisting in a timely delivery, adherence to objectives, and overall success in construction and engineering projects.
PS-4233 | How Recommended Practices for Project Scheduling are Becoming Obligations by Project Contracts | Saeid Khademagha, PEng PSP; Ali Yazdani, PEng | 2024 | In the last few decades, having an accurate and reliable project schedule as a technical tool for planning, managing, and controlling the time and cost of projects has become increasingly apparent across all industries. Project contracting parties have been trying to structure and discipline the process and procedure of project scheduling and performance measurement by putting industry-accepted principles and recommended practices into practice. Given the obvious benefits of such recommended practices, some project owners, especially in the public sector, are trying to contractually make them fully or partially enforceable and necessary for contractors to prepare various types of schedules (such as proposal, baseline, progress, recovery, and revised schedules, as well as schedule delay analysis) by including several pertinent clauses and provisions in their contracts for various attributes. In this article, the stipulated contractual requirements for some of the main components of the project Scheduling Procedure and their related essential actions will be discussed by reviewing different clauses in the contracts of the case study projects.
PS-4236 | Correcting Out-of-Sequence Logic | Ronald M. Winter, PSP FAACE | 2024 | Out-of-sequence logic occurs when actual status is applied to a planned CPM schedule. If the actual start date is earlier than the calculated early start date, then the actual date overrides logic. Depending on how the CPM calculation handles this occurrence, the remaining portion of the planned work may be delayed to re-enforce the planned logic. Studies show that approximately 40% of all started activities in typical construction projects are started out-of-sequence. Most schedulers say that they ‘fix’ any out-of-sequence activity in schedule updates by modifying the activity or logic. This effort may be misinformed as many schedulers do not fully appreciate the number of out-of-sequence occurrences in their schedules. For example, P6 Professional software only reports on active, direct out-of-sequence activities. This is a small percentage of the actual out-of-sequence in a schedule. Besides, they may be fixing the wrong logic as the indirect out-of-sequence (which P6 Professional does not report) may be the correct activity to fix. This paper looks into the reasons, methods, and pitfalls involved in correcting out-of-sequence logic during updates. Definitive rules are proposed for various categories of out-of-sequence conditions presented in earlier papers.
PS-4241 | The Top Ten Approaches to Avoiding Resource-Related Claims | Glen R. Palmer, CFCC PSP FAACE; Christopher W. Carson, CEP DRMP PSP FAACE | 2024 | Schedules are developed based on durations and quantities, sequenced as necessary, and durations are estimated based on production rates and quantities. Production rates are a function of resources, and many projects have failures in meeting project durations based on lack of or application of appropriate resources as well as claims related to cost overruns also due to resources. Since resources are at the heart of many failures and disputes winding up in claims, a useful approach to project controls is to identify these claims and develop methods to avoid claims. This paper is proactive, intended to avoid claims and not prove claims, so it focuses on ways to avoid resource-related claims through good planning and analysis. The authors have a long history of claims avoidance and resource analysis, as well as developing resource related claims, so they understand the issues and recognize the symptoms of resource claims. This paper will provide another paper in the popular “top ten” series that the authors have written to help project controls practitioners avoid project failures and claims.
PS-4267 | Planning and Scheduling for Workplace Safety | Mark David Smith; Daniel P. Gilmour, PSP; Matthew Smith | 2024 | Often considered conflicting obstacles to each other’s success, workplace safety and project scheduling are not the foes they were once thought to be. This paper will examine how traditional planning and scheduling processes affect workplace safety and how workplace safety measures may affect planning and scheduling. Authored by seasoned experts from the building construction industry with specialties in both scheduling and safety, this paper will also outline the correlation between site safety and schedule performance.
PS-4315 | Schedule Development and Progress Measurement Requirements for Fixed-Price Construction Contracts | Ricardo Albeny, CCP EVP | 2024 | Many bidders complain about rigid and detailed requirements for schedule development and progress measurement included in the owner’s bid documentation for a fixed-price contract. These requirements are typically laid out in the request for proposal (RFP) package, covering the full gambit of expectations ranging from safety, quality and, of course, project controls. The nature of these challenges typically stems from certain team members having a misconception about the level of detail that can or even should be asked of bidders in such a contractual arrangement. This viewpoint can often be characterized with phrases such as: “we don’t typically ask for that” or, “that seems too detailed for a lump-sum job”. This paper is going to reinforce the importance of ensuring such requirements are included in the bid documentation, while providing an additional purpose for these deliverables (schedule and progress measurement system) on fixed-price contracts, which relates to planning/assessing the payment amounts throughout the execution of the contract.
PS-4342 | A Statistical Approach to Developing Empirical System Durations for Wastewater Treatment Plants | Shreyas Raghavendra; Christopher W. Carson, CEP DRMP PSP FAACE | 2024 | Schedule overruns are a major challenge in the construction and rehabilitation of wastewater treatment plants (WTPs). This can often lead to cost overruns, loss of productivity, construction quality problems, large punch lists, disputes, and claims. This paper aims to develop empirical system durations for WTPs through the compilation of real-world WTP related as-planned and as-built schedule data and carry out regression analysis to model the relationship between the factors that affect the system durations (such as the size of the plant, the type of treatment process, and the age of the plant) and the system duration itself. This model can then be used to predict system duration based on the identified factors. The results of the study can be used to improve the accuracy and reliability of WTP schedules by pre-emptively informing planners and schedulers about the numerous factors affecting WTP construction and providing them with empirical system durations which can be used as a reference point. This will help to set realistic stakeholder expectations, reduce the risk of schedule and cost overruns.
PS-4354 | An Efficient Approach to Scheduling Repetitive Projects | Christopher W. Carson, CEP DRMP PSP FAACE | 2024 | Many projects consist of strings of activities that are repeated multiple times to generate the full schedule, a good example being a multi-story building. The foundation is subdivided into similar sections, comprised of excavation, layout, pile driving, pile cutoffs, pile caps, grade beams, and backfill. A common approach is to develop the first section and duplicate it, changing the horizontal label, or elevated floors in a vertical environment. This is quick and provides good quality control if done correctly. The risk to this effort is that the schedule development session is used to establish the standard fragnet in the first section and the sequencing between sections, then duplicated and validated by the construction management team, however, when the full schedule is reviewed, it commonly is not acceptable. This can be because the team has a gut feeling about the overall duration of the entire foundation or the full multi-story facility. The author worked out an approach that improves this method and minimizes the rework necessary when the final product is not acceptable because that rework might be only 15 changes on the first elevated floor but 300 changes for a twenty-story highrise. It can be faster to delete all the duplicated floors, make the changes on the single floor and duplicate it again. This paper will demonstrate the process to enable a standardized approach for an efficient schedule development process which the author calls an “outline schedule development.”
PS-4358 | An Overview of Hydropower Projects in Canada Part 2 (Spillway) | Ali Montaser, PEng CCP EVP PSP; Ahmed Montaser, EVP | 2024 | Canada is the world's fourth largest generator of electrical hydropower with facilities that have been around for more than one hundred years. Hydropower projects are inherently complex and building them in Canada has an additional layer of challenges due to typically being in remote locations, and having to face severe weather conditions that could reach as low as –50 C degrees. This paper is the second of a series that will provide an in-depth review of specific considerations related to hydropower projects in Canada. The first paper, “An Overview of Hydropower Construction Projects in Canada and Lessons Learned” was published at the 2023 AACE Conference & Expo 2023 (PM-4071).[26] This paper will focus on spillway construction, planning, and scheduling. It will also describe the author’s lessons learned based on their experiences related to such projects. The paper will do a deep dive into the execution strategy of the spillway complex. Then it will present the design of a schedule intelligent calendar that automatically changes the activity’s duration according to the season in which the activity is occurring. Lastly, it presents tried-and-true coding and sequencing methods for different concrete placement activities.
PS-4360 | (Panel Discussion) 100 Years of Federal Project Scheduling Insights and Lessons Learned | Michael R. Nosbisch, CCP PSP FAACE; Diane Bragoni, PSP; Patricia Bolton, PE; S. Brian Kong, PE CCP; Dr. David T. Hulett, FAACE | 2024 | This will be an interactive conversation with seasoned industry and government experts who bring more than ten decades of scheduling experience for complex federal projects/programs spanning from aerospace and defense to construction. This discussion will dive into key scheduling challenges, offering firsthand insights and actionable recommendations for professionals involved in federal projects and programs. Topics will include schedule resource and cost loading, level of detail, impacts and delays, reserve and contingencies, risk analysis, and more. Join this discussion to: - Directly engage with top professionals. - Actively participate, ask questions, and get immediate answers. - Elevate your understanding with real-world lessons and guidance.
PS-4377 | Addressing Schedule Complexity and Optimizing Scheduling Process for Infrastructure Projects | David A. Chigne, CCP CEP PSP; Shrutika Barwal, PSP | 2024 | Effective project scheduling is essential for the successful execution of any project. It serves as a fundamental tool to ensure that projects are completed within their designated timelines, and budget constraints, and with minimal disruptions. However, current requirements in the construction industry present a landscape of scheduling challenges. Various aspects, such as multiple calendars, constraints, lags, resource allocation, and even budget considerations, introduce complexity that can render schedules highly sensitive to changes. Even minor modifications can trigger cascading effects, significantly impacting project timelines, and making schedules difficult to interpret. This paper closely examines the process of integrating contractual requirements into project schedules with the help of a case study on an infrastructure project to illustrate how this alignment introduces complex scheduling challenges, influencing the critical path, near-critical paths, and/or driving paths for special milestones on different stages of the project. The goal is to develop a comprehensive understanding of how these complexities underscore the necessity for project schedulers and stakeholders to collaborate effectively, creating schedules that faithfully represent project complexity while fully harnessing the capabilities of the scheduling software.
PS-4387 | Mastering Risk Factors for Renewable Energy Projects So You Don’t Get Burnt, Blown Away, or Washed Out | Matthew D. Baker; Christopher J. Brasco; Dakus Gunn; James F. Timko | 2024 | Renewable energy projects pose unique scheduling challenges affecting project planning, delivery, and claims resolution. Solar, wind, and hydroelectric projects each involve distinctive supply, sequencing, environmental, means and methods, and risk shifting considerations. These performance exposures must be considered when initially scheduling and then evaluating delays on renewable energy projects. This paper addresses relevant considerations impacting the scheduling of renewable energy projects, provides input on how these considerations practically affect the development of the project schedule, and outlines strategies for mitigating associated risks. As the green energy transition accelerates, renewable energy projects are expected to constitute a growing percentage of the construction pipeline. Appreciating the unique scheduling challenges posed by such projects will help ensure that “you don’t get burnt, blown away, or washed out” on a renewable energy project.
PS-4415 | (Presentation Only) Schedule Analysis Best Practices for Capital Projects | Dave Ingalls, EVP | 2024 | Capital Infrastructure projects are often impacted by challenges in executing schedules per the plan, leading to unforeseen and costly delays to delivery milestones. In many cases, these delays are driven by the complexity of large, dynamic acquisition efforts. However, in some cases delays are simply caused by a failure to follow project planning best practices in the schedule development phase. This presentation aims to cover both the content of Integrated Master Scheduling (IMS) best practices as well as the impact “for better and for worse“ inherent in the rigor of that approach. Topics addressed will include approaches for the effective creation and baselining of a project IMS, in addition to best practices for schedule management and schedule analysis in the execution phase. Key metrics for both elements will be covered in order to provide a quantitative anchor of this discussion.
PS-4470 | Automatic Train Control – Technical Challenges and Project Controls | Dr. Achintyamugdha Sharma; Dr. Priyanka Deka; Goutam Jois, Esq.; Umesh K. Jois | 2025 | Different types of projects and programs can result in tangible differences in scheduling and project controls processes. The planning and scheduling community may face unique challenges in the case of automatic train control and other railroad projects. The rail transit industry invests heavily in its infrastructure to ensure efficiency and safety of millions of commuters. Federal agencies like the Federal Railroad Administration (FRA), Federal Transit Administration (FTA) and various transit agencies across the US have prioritized the implementation of positive train control (PTC) to enhance commuter safety. For increased frequency of trains and efficiency of dispatch, systems like communications based train control (CBTC) are implemented on railroads. These highly specialized systems and their complex implementation on the wayside, onboard rail cars, and back offices and central dispatch centers of the railroads are accompanied by unique challenges. Some of these challenges include interoperability among different railroads, reliance on strict outages, highly proprietary software and hardware systems uniquely customized for specific systems, and a small pool of qualified contractors to perform such kind of work. These in turn pose significant challenges to planning the sequence of activities and schedule durations accurately, which in turn lead to extension of time and claims in projects. In this paper, the challenges associated with train control type projects from planning, scheduling, risk management and project controls standpoint are presented.. Additionally, a model is proposed to predict the duration of activities more accurately for train control type projects.
PS-4497 | Challenges and Framework for Subcontractor Schedule Development and Management | Dr. Pei Tang, PRMP PSP; Huimin Shi, CCP PSP; Tianxiong Yang, PE; Abraham Naim, PE PSP | 2025 | Effective subcontractor schedule development and management are critical to the success of large construction projects. This paper delves into the essential components of subcontractor schedule development, with a particular focus on the challenges associated with baseline schedule creation, schedule updates, and lookahead schedule planning. Drawing from extensive experience, it presents lessons learned and strategies for managing subcontractors' real planning processes and addressing delays. The integration of subcontractor schedules into the overall project timeline is examined, along with best practices for fostering collaboration between the general contractor (“GC”) and its subcontractors. Additionally, the paper explores the common challenges subcontractors face during change management and offers practical solutions for both subcontractors and the GC to improve project progress management. By providing a comprehensive framework, this paper aims to equip project managers from both the GC and subcontractors with the tools necessary to enhance performance, ultimately ensuring the successful completion of construction projects.
PS-4506 | Prospective Time Impact Analysis The Perfectly Imperfect Theory | Savannah Kleyla, PSP; John S. Crane, CFCC PSP | 2025 | In contemporary project management, a time impact analysis (TIA) is often required for evaluating delays in a project's timeline. Many may know the concerns with performing a retrospective TIA when analyzing project delays. However, they may not realize that some of the same concerns still apply when performing a prospective TIA. This research aims to unveil the underlying intricacies of TIA’s, shedding light on often-overlooked nuances and fallacies. Drawing from publications and examples, this paper will highlight the critical factors influencing the effectiveness and accuracy of a prospective TIA. While a prospective TIA is an indispensable tool for forecasting project delays, its accuracy is contingent upon a comprehensive understanding of the project's status, contract requirements, and clarity of the change. All too often there is a gap between the theoretical model and the practical implementation that could potentially obscure other impacts on the project.
PS-4515 | Exposing the Risks of Progress Override and Actual Dates in Delay Analysis | John Coker, PSP; John Cleary, PSP | 2025 | This paper examines Oracle P6 critical path method (CPM) calculation settings. In particular, it examines the effects of using progress override and actual date calculations in engineering, procurement, and construction (EPC) scheduling, particularly in the context of forensic delay analysis. By utilizing a real case study that applies retained logic calculations and comparing it with hypothetical scenarios employing progress override and actual date calculations, the analysis demonstrates how these alternative settings can distort outcomes. The findings underscore the importance of adhering to retained logic to ensure accurate and reliable delay analysis results. Practical examples and detailed comparisons further highlight the misleading nature of progress override and actual date calculations, offering clear guidance for real-world application.
PS-4551 | Utilizing AutoCAD and Excel to Generate a Linear Schedule | Huimin Shi, CCP PSP; Benjamin Chan; Matt Kolb | 2025 | There exists various software on the market for schedulers to develop linear schedules. This paper presents a procedure in which a contractor can utilize AutoCAD to generate a linear schedule. The generation of the schedule is automated with the assistance of an Excel spreadsheet. The usage of AutoCAD with Excel provides a visualization platform which is modular and accessible. This allows the contractor to analyze risks, conflicts, and opportunities within the schedule.
PS-4555 | The Top Ten Mistakes Made in Planning a Complex EPC Project | Glen R. Palmer, CFCC PSP FAACE; Christopher W. Carson, CEP DRMP PSP FAACE | 2025 | Many of the problems that arise during construction are just symptoms of the original problems related to poor planning. If a project is planned in detail with the right stakeholders, it will survive most challenges with minor revisions or actions. Failure to plan or mistakes made in planning result in delays, inefficiencies, disruption, and increase the management needed during construction. In this paper, the authors will describe the top ten mistakes usually made in planning a complex construction project. The paper will explain why each of these ten mistakes leads to later failures and how to perform this aspect of planning in a more efficient and successful way to ensure a better project plan. The authors have a long history of planning projects that have resulted in projects with collaborative project teams, a viable project plan, and on-time project delivery.
PS-4556 | Owners, Don’t Let Your Modeled Forecasts Grow Up to be Absorbed Claims | Christopher W. Carson, CEP DRMP PSP FAACE; Mark C. Sanders, PE CCP CFCC PSP | 2025 | Owners commonly choose fixed price contracts to transfer time and cost performance risk to the contractor based on an estimated cost and duration. When scope is changed, additional money and time may be required for performance of the contract, and typically contractors provide a cost estimate for the scope change prior to performing the work. Similarly, when the project is delayed, contractors are asked for a schedule model and estimate of any additional time required. Once the additional time and cost for performance are negotiated, the change order formally transfers the risk of performance of the changed scope, and the contractor is left to optimize performance to achieve or improve profit. However, it is common for time extension negotiations to be prolonged or fail entirely, and the changed scope begins or even completes without knowing whether a time extension will be granted. Failing to negotiate time extensions timely leaves the performance risk on the owner, who loses the opportunity to assign the risk to the contractor, as was done in the original contract. The analysis required to resolve the time extension shifts from a prospective model of the estimated impact to a forensic determination of the actual impact once delay is absorbed. This paper details the benefits of negotiating time extensions prospectively and provides guidance on successfully transitioning from modeled to observational delay analysis if those negotiations are not concluded timely.
PS-4576 | Quantitative Schedule and Cost Risk Analysis on Critical Path Method (CPM) Schedule | Abbas Saifi, PEng CCP EVP PSP; Greg M. Hall, PSP | 2025 | Project success relies on proper upfront planning, cost projection, and execution. This requires an accurate and realistic project schedule and estimate representing the project plan and budget. The CPM schedule is developed to meet the owner’s milestone and completion dates but cannot incorporate the uncertainty of activity durations. These activity durations are set on some assumptions, which, over time, are forgotten, and the logic-duration-driven dates are presumed to be definitive rather than conditional statements. This paper aims to predict the risks and uncertainties in activity duration and derive the implications for the project schedule and cost. It will also show the likelihood of a project meeting the planned dates and the required time and cost contingency to overcome the identified risks in the schedule.
PS-4585 | Maximizing Schedule Effectiveness: A Guide to Resource and Cost Loading Methodologies | Delbert E. Bearden, PSP | 2025 | This paper presents a comprehensive guide to resource and cost loading methodologies for maximizing schedule effectiveness in engineering, procurement, and construction projects. It examines the advantages of resource and cost loaded schedules, including enhanced project performance indicators, improved resource management, and better decision-making capabilities. The study compares two primary approaches for integrating resources and costs into schedules: using the official project estimate with its task-based breakdown and utilizing the schedule of values (SOV) with its specification section breakdown. It explores the challenges and benefits of each method, as well as techniques for combining these approaches to create accurate resource-loaded schedules. The paper discusses best practices for integrating the work breakdown structure (WBS), schedule, and cost estimate, ensuring consistency across project control documents. It covers schedule optimization techniques, including resource leveling and critical path analysis in resource-constrained environments. The study also delves into the process of estimating activity durations using various methods and formulas derived from estimates or SOV. Detailed sections on resource and cost loading methodologies provide step-by-step guidance, including the use of lump sum cost resources and the implementation of cost accounts. The paper addresses the challenges of aligning detailed estimates, SOV, and schedule activities, offering strategies for reconciliation and maintenance. Through practical examples and case studies, the paper demonstrates the application of these methodologies across different project phases. It also covers advanced topics such as schedule validation, change management, and the use of earned value management for forecasting and trend analysis. The final sections focus on data visualization techniques, providing guidance on creating effective resource histograms and cost charts, including cumulative S-curves and earned value charts. While examples are primarily based on Primavera P6, the paper emphasizes the applicability of these concepts across various scheduling software platforms. By offering a comprehensive examination of resource and cost loading methodologies, this paper aims to equip project controls professionals with practical knowledge to enhance project performance, promote accurate forecasting, improve resource management, and increase project success rates in complex project environments.
PS-4607 | Implementing Duration Overrun Analysis for Schedule Review and Forecasting | Christopher W. Carson, CEP DRMP PSP FAACE; Antoine Bechaalani, PSP; Shreyas Raghavendra | 2025 | Evaluation of activity duration overruns serves as a crucial measure for evaluating efficiency and productivity in project schedules, offering valuable insights into the comparison between actual performance and planned durations. This was originally introduced to the industry as a software package called “Tipper” as slang for “TPR” (time performance ratio) and the authors have since reproduced the concept in independent calculations. This paper provides a comprehensive guide on TPR calculation and showcases its practical significance in schedule analysis and modeling. This research emphasizes the utility of TPR in assessing productivity challenges, effects of delays, and modeling schedule projections. Further, this paper also provides a comprehensive guide, along with examples, for calculating TPR from completed activities on the critical and near-critical paths, averaging the TPR for each trade, bid package, area or location and applying this to the remaining critical path activities enabling accurate forecasting of project completion dates and identification of time saving opportunities. The inclusion of case studies illustrates how TPR enhances project forecasting, aids in recovery efforts, optimizes critical path scheduling, and improves overall project efficiency. Focused on practical relevance, the paper aims to empower project managers, schedulers, and forensic analysts with a structured approach to incorporating TPR into project control processes, leading to more informed decision-making, proactive risk mitigation, and greater schedule optimization.
PS-4630 | The Evolution of Scheduling Practices: Gantt Charts to CPM and Beyond! | Teja Pulla, CCP CEP EVP PRMP PSP; Christopher W. Carson, CEP DRMP PSP FAACE; Dr. Vijayeta Malla | 2025 | Project scheduling has evolved significantly since its inception from fundamental visual tools to advanced systems. This paper traces the methodological progression, beginning with early 20th-century scheduling innovations such as the Gantt chart for task management. The mid-20th century introduced the critical path method (CPM) and program evaluation and review technique (PERT) to identify critical tasks and optimize timelines. Advancements including building information modeling (BIM) and artificial intelligence (AI) which further refined scheduling practices allowing for dynamic project planning and predictive analysis. This paper explores historical developments, technological advancements, and future trends while identifying the needs driving development, demonstrating how the evolution of project scheduling practices has improved project outcomes and efficiency.
PS-4644 | Complexities of Evaluating Recovery Schedules in a Forensic Delay Analysis | Eric Schatz, PE CFCC PSP; Phillip Kenny; Haswanth Venkatavijayan | 2025 | The preparation of a recovery schedule during construction is a critical process with significant implications. The decision to revise the as-planned schedule to reflect considerable changes in a project’s timeline, sequencing, and resources can cause later complications when evaluating delays after the fact. This paper is intended both for those preparing a recovery schedule, to be aware of potential unintended future implications, as well as those evaluating delays forensically on a project that includes recovery schedules. As is the case with many forms of forensic analyses, corroborated, contemporaneous documentation is essential for a complete evaluation. Ultimately, if a contractor does not achieve its recovery plan for a variety of potential reasons, the question arises whether the delays and responsibility should be measured from the original plan, the recovery schedule, or some other approach. In other words, does a recovery schedule erase the sins of the past? When performing a basic contemporaneous period analysis, the answer may appear to be yes. This paper explores various scenarios to help navigate the complexities of validating recovery schedules in forensic analysis, including the impact of timing, actual progress, and sequencing.
PS-4652 | Effective Management and Scheduling of Working Day Contracts | Avi Sharma, PSP; Matthew G. Nichols, PSP; Diego Melchert, PSP | 2025 | This paper provides an overview of key considerations in the implementation and management of working day contracts. It begins by examining the fundamental purpose of such contracts and their associated language, including illustrative examples from the Colorado Department of Transportation (CDOT) and the Illinois Department of Transportation (IDOT). This paper then examines scheduling aspects of working day contract projects, including the alignment of the baseline schedule with the contract and updating progress schedules. It further explores the challenges encountered in the implementation of working day contracts, like consistent application of day-charging standards, keeping records of charged days, and managing schedule acceleration. Additionally, it covers the analysis of working day contract schedules, focusing on identifying the critical path. Lastly, this paper offers practical recommendations from the authors for effectively implementing working day contracts.
PS-4656 | Bridging the Divide: Integrating EPC Schedules to Minimize Delays in Complex Projects | John Coker, PSP; Khaled Aziza, EVP PSP; Evan Lee | 2025 | This paper introduces the common engineering, procurement, and construction (EPC) contract structures and the risk allocations for project parties through different project phases. The paper also explores the challenges and practices for aligning EPC schedules in complex projects involving multiple contractors. While schedule misalignment may not directly cause delay, it significantly complicates the quantification and assignment of delay responsibilities. Issues such as inconsistent design timelines and unaccounted-for material deliveries exacerbate these challenges, often leading to disputes and inefficiencies. Through a case study, this paper highlights the critical importance of early schedule alignment and provides practical recommendations and lessons learned to project stakeholders for enhancing schedule integration and reducing the risk of delays.
PS-4683 | Key Scheduling and Reporting Requirements for Collaborative Contracts | S. Farzad Moosavi; Ronn Chester Baluyot; Ashraf Nabil Ibrahim Fahim | 2025 | Baseline schedules are among the most important deliverables developed and maintained during the life cycle of projects. Baselines are used for tracking, progress reporting, recovery and scenario planning, and are the backbone of any dispute resolution effort. The first step is ensuring that the schedule fits the purpose of a project by enforcing the right schedule requirements in the contract. On the other hand, considering difficulties experienced with traditional project delivery models, there has been a shift towards collaborative contracts as an alternative. The collaborative model requires a more cooperative engagement between parties. This paper presents the key schedule and reporting requirements that are recommended to be included in construction contracts based on practical experience gained through the execution and audit of a variety of construction projects in different sectors of the industry. This article focuses on the requirements for the collaborative contracting model. The requirements presented will be protecting the best interests of the project as the authors took a neutral position and did not put any side of the contract above other parties. These requirements are expected to increase transparency, foster collaboration between parties, and support effective communication of critical information in a timely manner. The rationale behind each requirement is also discussed in this article.